## ISO log
CONSTRUCTION PACKAGE NO. | ISO NUMBER |  |  | REV | COMMENTS | ORIGINAL DRAWING | [17 empty] | COMMENTS | BACK DRAFT DRAWING | [6 empty] | 2ND BACK DRAFT DRAWING | [5 empty] | TO SQUAD CHECK | TO STRESS | ISSUE COPY FOR SIGNATURE |  |  |  |  | SIGNED ISSUE PLOTS | REV | COMMENTS | DATE RECEIVED | SIGNED ISSUE PLOTS | REV | COMMENTS | DATE RECEIVED | SIGNED ISSUE PLOTS | REV | COMMENTS | DATE RECEIVED | SIGNED ISSUE PLOTS
[6 empty] | DSGNR | DATE RECEIVED | MAT'LS CHECK |  | BERMAC CHECK |  | PIPING CHECK | [8 empty] | AREA LEAD |  |  |  | PIPING BACK-CHECK |  |  |  | AREA LEAD |  |  | PIPING BACK-CHECK |  | APPROVED OR DISAPPROVED | AREA LEAD |  |  |  |  | PIPING |  | STRESS |  | ENG'R
| UNIT No. | LINE No. | SHT No. |  |  |  |  | OUT | IN | OUT | IN | OUT |  |  |  | IN |  |  | PIPING COPY SENT TO STRESS FOR 2nd REVIEW | APPROVED OR DISAPPROVED | OUT |  | IN | (REASON FOR HOLDS) | OUT | CHKR | IN | APPROVED OR DISAPPROVED | OUT |  | IN | OUT | IN |  | OUT |  | IN |  |  | OUT | IN | OUT | IN | OUT | PCF FILES ISSUED TO DOC CTRL |  |  |  | OUT TO DOCUMENT CONTROL |  |  |  | OUT TO DOCUMENT CONTROL |  |  |  | OUT TO DOCUMENT CONTROL
[12 empty] | CHKR | ORIG | RETURNED COPIES FROM
[14 empty] | MAT'LS | BERMAC | ORIG | MAT'LS | BERMAC |  |  | LEAD | FOR BACKDRAFT | [6 empty] | LEAD | FOR BACKDRAFT |  |  |  |  | LEAD | FOR BACKDRAFT
2 | 1107-MD | DF-1001 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
1 | 1501-AR | DF-1001 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
2 | 1107-MD | DF-1002 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | HOLD W/ AK |  | HOLD W/ AK |  | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
3 | 1801-AR | DF-1003 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1801-AR | DF-1005 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 | 2007-02-14 | 2007-02-20 | W/ KY | 2007-02-20 | 2007-02-22 | 2007-02-20 | [21 empty] | 2007-03-30
4 | 2101-AR | DF-1005 | 1 | 0 |  | AZ | 2007-02-23
4 | 2101-AR | DF-1005 | 2 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
1 | 1503-AR | DF-1007 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | DF-1008 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | DF-1009 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | DF-1010 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | DF-1011 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | DF-1012 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
4 | 1303-AR | DF-1013 | 3 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1304-AR | DF-1013 | 1 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1306-MD | DF-1013 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1401-MD | DF-1014 | 1 | 0 | HOLD-PIPING TO BE REDESIGNED | [6 empty] | WAP |  |  |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | DF-1015 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | DF-1015 | 1 | 0 | HOLD-PIPING TO BE REDESIGNED | [6 empty] | WAP |  |  |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1405-MD | DF-1016 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 |  | 2007-01-29 | 2007-01-29 |  |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1405-MD | DF-1017 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 |  | 2007-01-29 | 2007-01-29 |  |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1405-MD | DF-1018 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 |  | 2007-01-29 | 2007-01-29 |  |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1402-AR | DF-1019 | 1 | 0 |  | RO
4 | 1405-MD | DF-1019 | 1 |  |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 |  | 2007-01-29 | 2007-01-29 |  |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
2 | 1107-MD | DF-1020 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | DF-1021 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | DF-1022 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1303-AR | DF-1024 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
[8 empty] | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A
4 | 1404-MD | DF-1025 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1404-MD | DF-1026 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1404-MD | DF-1027 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1404-MD | DF-1028 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | DF-1029 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | DF-1030 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1402-AR | DF-1030 | 1 | 0 |  | RO
4 | 1401-MD | DF-1030 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | DF-1031 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | DF-1032 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
3 | 1701-AR | DF-1033 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-AR | DF-1033 | 2 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-AR | DF-1033 | 3 | 0 |  | AZ | 2007-02-07 | [29 empty] | 2007-03-30
3 | 1701-AR | DF-1034 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-AR | DF-1034 | 2 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | DF-1035 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | DF-1036 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | DF-1037 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | DF-1038 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-AR | DF-1038 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
|  | DF-1039 | 1 | 0
|  | DF-1040 | 1 | 0
3 | 1701-AR | DF-1042 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
2 | 1107-MD | DF-1043 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1302-AR | DF-1044 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
2 | 1107-MD | DF-1044 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1302-MD | DF-1044 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | AK | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 | 2007-01-08 | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
2 | 1107-MD | DF-1045 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  | 2007-01-08 | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | DF-1047 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | DF-1048 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | DF-1049 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-09 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | DF-1050 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-09 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | DF-1051 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
1 | 1503-AR | DF-1052 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | DF-1052 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | DF-1053 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | DF-1053 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | DF-1054 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | DF-1054 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1502-AR | DF-1055 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1502-AR | DF-1055 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1502-AR | DF-1056 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1502-AR | DF-1056 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1502-AR | DF-1057 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1502-AR | DF-1057 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1502-AR | DF-1058 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1502-AR | DF-1058 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1502-AR | DF-1059 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1502-AR | DF-1059 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1502-AR | DF-1060 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1502-AR | DF-1060 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1501-AR | DF-1061 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1501-AR | DF-1061 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1501-AR | DF-1062 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1501-AR | DF-1062 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | DF-1064 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | DF-1066 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | DF-1066 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
4 | 1304-AR | DF-1067 | 1 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
|  | DF-1068 | 1 | 0
2 | 1107-MD | DF-1070 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
1 | 1501-AR | DF-1071 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
2 | 1107-MD | DF-1072 | 1 | 0 | NEW | JJL | 2006-12-14 | [17 empty] | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | DF-1073 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | DF-1074 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | DF-1075 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | DF-1076 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
1 | 1501-AR | DF-1077 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1501-AR | DF-1077 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1501-AR | DF-1078 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1501-AR | DF-1078 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1601-AR | DF-1079 | 1 | 0 |  | JJL | [30 empty] | 2007-03-30
2 | 1107-MD | DF-1080 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1403-AR | DF-1081 | 1 | 0
4 | 1404-MD | DF-1081 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
2 | 1107-MD | DF-1082 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1307-MD | DF-1083 | 1 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 |  |  | HT | 2007-02-08 | 2007-02-20 | [12 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
2 | 1101-AR | DF-1083 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
|  | DF-1091 | 1 | 0
3 | 1801-MD | DF-9014 | 1 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1801-MD | DF-9014 | 2 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1801-MD | DF-9014 | 3 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1801-MD | DF-9014 | 4 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1801-MD | DF-9014 | 5 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1801-MD | DF-9014 | 6 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1801-MD | DF-9014 | 7 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1801-MD | DF-9014 | 8 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
4 | 1402-AR | DP-1501 | 1 | 0 |  | RO
4 | 1402-MD | DP-1501 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 |  |  | WAP | 2007-01-19 | 2007-01-26 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
|  | DP-1502 | 1 | 0
4 | 1303-AR | DP-1503 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1306-MD | DP-1503 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1302-AR | DP-1504 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1303-AR | DP-1504 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1306-MD | DP-1504 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1304-AR | DP-1505 | 1 | 0 |  | GM | [30 empty] | 2007-03-30
4 | 1306-MD | DP-1505 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1306-MD | DP-1505 | 2 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1306-MD | DP-1506 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1401-MD | DP-1507 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | DP-1508 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | DP-1509 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | DP-1509 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1304-AR | DP-1510 | 1 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1306-MD | DP-1510 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 | 2006-12-21 | 2007-01-29 | AK | 2006-12-21 | 2007-01-02 | 2007-01-29 | 2007-02-05 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1306-MD | DP-1510 | 2 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1301-MD | DP-1511 | 1 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | 2006-11-20 | 2007-01-15 | AK | 2006-11-20 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-04-10
4 | 1302-AR | DP-1511 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1301-MD | DP-1511 | 2 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | - |  | AK | 2006-11-20 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | DP-1512 | 1 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | DP-1512 | 2 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  | 2006-12-18 | 2007-01-15 | AK | 2006-12-18 |  | 2007-01-15 | 2007-01-26 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | DP-1512 | 3 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-AR | DP-1513 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1303-MD | DP-1513 | 1 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | AK | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1303-MD | DP-1513 | 2 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | AK | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1402-AR | DP-1514 | 1 | 0 |  | RO
4 | 1402-AR | DP-1515 | 1 | 0 |  | RO
4 | 1405-MD | DP-1514 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 |  | 2007-01-29 | 2007-01-29 |  |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1402-MD | DP-1515 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 |  |  | WAP | 2007-01-19 | 2007-01-26 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
|  | DP-1516 | 1 | 0
|  | DP-1517 | 1 | 0
4 | 1304-AR | DP-9026 | 1 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1304-AR | DP-9026 | 2 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1304-AR | DP-9026 | 3 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1304-AR | DP-9026 | 4 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1304-AR | DP-9026 | 5 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1304-AR | DP-9026 | 6 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1304-AR | DP-9026 | 7 | 0 |  | GM | 2007-03-02 | 2007-03-30 | [28 empty] | 2007-03-30
4 | 1304-AR | DP-9026 | 8 | 0 |  | GM |  | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 2101-AR | DU-2002 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | DU-2003 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | DU-2004 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | DU-2005 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | DU-2006 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | DU-2007 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | DU-2008 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | DU-2009 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
1 | 1601-AR | DU-2010 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | DU-2011 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | DU-2013 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | DU-2014 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | DU-2016 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | DU-2017 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | DU-2019 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | DU-2020 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1503-AR | DU-2022 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1503-AR | DU-2023 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1502-AR | DU-2024 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1502-AR | DU-2025 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1502-AR | DU-2026 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1501-AR | DU-2027 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
|  | DU-2028 | 1 | 0
|  | DU-2029 | 1 | 0
|  | DU-2030 | 1 | 0
|  | DU-2031 | 1 | 0
|  | DU-2032 | 1 | 0
|  | DU-2033 | 1 | 0
|  | DU-2034 | 1 | 0
|  | DU-2035 | 1 | 0
|  | DU-2036 | 1 | 0
4 | 1402-AR | DU-2031 | 1 | 0 |  | RO
4 | 1402-AR | DU-2032 | 1 | 0 |  | RO
4 | 1402-AR | DU-2033 | 1 | 0 |  | RO
4 | 1402-AR | DU-2034 | 1 | 0 |  | RO
4 | 1402-AR | DU-2035 | 1 | 0 |  | RO
4 | 1402-AR | DU-2036 | 1 | 0 |  | RO
4 | 1402-AR | DU-2037 | 1 | 0 |  | RO
4 | 1402-AR | DU-2038 | 1 | 0 |  | RO
4 | 1402-AR | DU-2039 | 1 | 0 |  | RO
1 | 1503-AR | DU-2040 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | DU-2041 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1601-AR | DU-2042 | 1 | 0 |  | JJL | [30 empty] | 2007-03-30
|  | DU-2043 | 1 | 0
1 | 1601-AR | DU-2044 | 1 | 0 |  | JJL | [30 empty] | 2007-03-30
4 | 2101-AR | DU-2045 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | DU-2046 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
1 | 1601-AR | DU-2047 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | DU-2048 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1501-AR | DU-2050 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1601-AR | DU-2051 | 1 | 0 |  | JJL | [30 empty] | 2007-03-30
4 | 1302-AR | GF-2501 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1307-MD | GF-2501 | 1 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 | 2007-02-08 | 2007-02-16 | HT | 2007-02-08 | 2007-02-20 | 2007-02-16 | [11 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-MD | GF-2502 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | AK | 2006-11-21 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1304-MD | GF-2503 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 |  |  | AK | 2006-12-13 | 2006-12-18 |  | 2007-01-24 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1304-MD | GF-2504 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 |  |  | AK | 2006-12-13 | 2006-12-18 |  | 2007-01-24 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1304-MD | GF-2504 | 2 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 | 2006-12-15 | 2007-01-15 | AK | 2006-12-13 | 2006-12-18 | 2007-01-15 | 2007-01-24 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1304-AR | GF-2505 | 2 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1304-MD | GF-2505 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 |  |  | AK | 2006-12-13 | 2006-12-18 |  | 2007-01-24 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1305-MD | GF-2505 | 1 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1306-MD | GF-2505 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1304-AR | GF-2506 | 1 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1304-AR | GF-2506 | 2 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
GF-2507
1 | 1503-AR | GF-2508 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | GF-2509 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | GF-2510 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | GF-2511 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | GF-2512 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | GF-2513 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
4 | 1303-AR | GF-2514 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
2 | 1107-MD | GF-2514 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1304-MD | GF-2514 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 |  |  | AK | 2006-12-13 | 2006-12-18 |  | 2007-01-24 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
2 | 1107-MD | GF-2515 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | GF-2516 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | GF-2517 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1304-MD | GF-2518 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 | 2006-12-15 | 2007-01-15 | AK | 2006-12-13 | 2006-12-18 | 2007-01-15 | 2007-01-24 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1303-AR | GF-2521 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1304-MD | GF-2521 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 |  |  | AK | 2006-12-13 | 2006-12-18 |  | 2007-01-24 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1306-MD | GF-2521 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 | 2006-12-21 | 2007-01-29 | AK | 2006-12-21 | 2007-01-02 | 2007-01-29 | 2007-02-05 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1303-AR | GF-2522 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
1 | 1501-AR | GF-2522 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
4 | 1306-MD | GF-2522 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
|  | GF-2523 | 1 | 0
|  | GF-2524 | 1 | 0
1 | 1503-AR | GF-2525 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | GF-2526 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | GF-2527 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | GF-2528 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | GF-2529 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | GF-2530 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | GF-2531 | 1 | 0 |  | DR | 2007-03-07 | 2007-03-07 |  | 2007-03-07 |  | DG | 2007-03-07 | [23 empty] | 2007-03-30
1 | 1503-AR | GF-2532 | 1 | 0 |  | DR | 2007-03-07 | 2007-03-07 |  | 2007-03-07 |  | DG | 2007-03-07 | [23 empty] | 2007-03-30
1 | 1502-AR | GF-2533 | 1 | 0 |  | DR | 2007-03-07 | 2007-03-07 |  | 2007-03-07 |  | DG | 2007-03-07 | [23 empty] | 2007-03-30
1 | 1502-AR | GF-2534 | 1 | 0 |  | DR | 2007-03-07 | 2007-03-07 |  | 2007-03-07 |  | DG | 2007-03-07 | [23 empty] | 2007-03-30
1 | 1502-AR | GF-2535 | 1 | 0 |  | DR | 2007-03-07 | 2007-03-07 |  | 2007-03-07 |  | DG | 2007-03-07 | [23 empty] | 2007-03-30
1 | 1501-AR | GF-2536 | 1 | 0 |  | DR | 2007-03-07 | 2007-03-07 |  | 2007-03-07 |  | DG | 2007-03-07 | [23 empty] | 2007-03-30
4 | 1302-MD | GF-2549 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | AK | 2006-11-21 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-MD | GF-2550 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | AK | 2006-11-21 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-MD | GF-2551 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | AK | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-03-14
4 | 1302-MD | GF-2552 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | AK | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-03-14
4 | 1302-MD | GF-2553 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | AK | 2006-11-21 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-AR | GF-2554 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1302-MD | GF-2554 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | AK | 2006-11-21 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
2 | 1107-MD | GF-2554 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1304-MD | GF-2555 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 |  |  | AK | 2006-12-13 | 2006-12-18 |  | 2007-01-24 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1304-MD | GF-2556 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 | 2006-12-15 | 2007-01-15 | AK | 2006-12-13 | 2006-12-18 | 2007-01-15 | 2007-01-24 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-03-14
4 | 1304-MD | GF-2557 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 | 2006-12-15 | 2007-01-15 | AK | 2006-12-13 | 2006-12-18 | 2007-01-15 | 2007-01-24 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-03-14
4 | 1304-MD | GF-2558 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 | 2006-12-15 | 2007-01-15 | AK | 2006-12-13 | 2006-12-18 | 2007-01-15 | 2007-01-24 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-03-14
4 | 1304-MD | GF-2559 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 |  |  | AK | 2006-12-13 | 2006-12-18 |  | 2007-01-24 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1304-MD | GF-2560 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 | 2006-12-15 | 2007-01-15 | AK | 2006-12-13 | 2006-12-18 | 2007-01-15 | 2007-01-24 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-03-14
4 | 1304-MD | GF-2561 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 | 2006-12-15 | 2007-01-15 | AK | 2006-12-13 | 2006-12-18 | 2007-01-15 | 2007-01-24 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-03-14
4 | 1304-MD | GF-2562 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 |  |  | AK | 2006-12-13 | 2006-12-18 |  | 2007-01-24 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1305-MD | GF-2563 | 1 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
|  | GF-2563 | 1 | 0
4 | 1304-AR | GF-2564 | 1 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1306-MD | GF-2564 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
|  | GF-2565 | 1 | 0
4 | 1303-AR | GF-2566 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
2 | 1107-MD | GF-2566 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1306-MD | GF-2566 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
2 | 1107-MD | GF-2567 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | GF-2568 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | GF-2569 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1303-AR | GF-2570 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
2 | 1107-MD | GF-2570 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | HOLD W/ AK |  | HOLD W/ AK |  |  |  | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | GF-2571 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-09 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | GF-2572 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-09 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | GF-2573 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
3 | 1701-MD | GF-2574 | 1 | 0 | NEW | AZ | 2007-01-24 | [15 empty] | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 |  |  | 2007-01-29 | BACKDRAFT - AZ |  | 2007-01-29 | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-AR | GF-2574 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
2 | 1101-AR | GF-2576 | 1 | 0 |  | JL
4 | 2101-AR | GF-2577 | 1 | 0 |  | AZ | 2007-02-23
4 | 2101-AR | GF-2577 | 2 | 0 |  | AZ | 2007-02-23
4 | 2101-AR | GF-2577 | 3 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
2 | 1101-AR | GF-2578 | 1 | 0 |  | JL
2 | 1101-AR | GF-2579 | 1 | 0 |  | JL
|  | GF-2580 | 1 | 0
|  | GF-2582 | 1 | 0
2 | 1107-MD | GF-2583 | 1 | 0 | NEW | JJL | 2006-12-14 | [17 empty] | 2006-12-14 | AK | HOLD W/ AK |  | HOLD W/ AK |  |  |  | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | GF-2587 | 1 | 0 | NEW | JJL | 2006-12-14 |  |  | 2006-12-15 | 2007-01-15 |  |  |  | 2007-01-15 | [9 empty] | 2006-12-14 | AK | HOLD W/ AK |  | HOLD W/ AK |  |  |  | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26 |  |  |  |  | 2 |  | 2007-05-11 | 2007-05-11
1 | 1503-AR | GF-2588 | 1 | 0 |  | DR | 2007-03-07 | 2007-03-07 |  | 2007-03-07 |  | DG | 2007-03-07 | [23 empty] | 2007-03-30
|  | GF-2588 | 2 | 0 | CHECK W DR-NOT ON FINAL 1503-AR | DR | 2007-03-07 | 2007-03-07 |  | 2007-03-07 |  | DG | 2007-03-07
4 | 1302-MD | GF-2590 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | AK | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-03-14
4 | 1302-MD | GF-2591 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | AK | 2006-11-21 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-MD | GF-2592 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | AK | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-AR | GF-2593 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1303-AR | GF-2593 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1302-AR | GF-2596 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1303-AR | GF-2596 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1303-MD | GF-2596 | 1 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | AK | 2006-11-23 | 2006-11-27 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1303-MD | GF-2597 | 1 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | AK | 2006-11-23 | 2006-11-27 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1304-AR | GF-2598 | 1 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
2 | 1101-AR | GF-2598 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
2 | 1107-MD | GF-2598 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
1 |  | GF-2599 | 1 | 0
1 | 1503-AR | GF-2600 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
4 | 1301-MD | GF-2602 | 1 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | 2006-11-20 | 2007-01-15 | AK | 2006-11-20 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-AR | GF-2602 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1307-MD | GF-2602 | 1 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 | 2007-02-08 | 2007-02-16 | HT | 2007-02-08 | 2007-02-20 | 2007-02-16 | [11 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1301-MD | GF-2604 | 1 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | - |  | AK | 2006-11-20 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1301-MD | GF-2605 | 1 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | - |  | AK | 2006-11-20 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
[8 empty] | 2006-11-20 | 2006-11-23 | 2006-11-20 | 2007-01-15 | AK | 2006-11-20 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A
4 | 1302-AR | GF-2606 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1303-AR | GF-2606 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1306-MD | GF-2606 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1301-MD | GF-2608 | 1 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | - |  | AK | 2006-11-20 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-AR | GF-2608 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
2 | 1107-MD | GF-2608 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-03 | 2007-01-03 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1302-MD | GF-2611 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | AK | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
|  | GF-2612 | 1 | 0
4 | 1307-MD | GF-2614 | 1 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 | 2007-02-08 | 2007-02-16 | HT | 2007-02-08 | 2007-02-20 | 2007-02-16 | [11 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-03-14
3 | 1701-MD | GF-2615 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 | 2007-01-12 | 2007-01-31 | WA | 2007-01-10 | 2007-01-16 | 2007-01-31 | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 |  |  |  |  | 2007-01-29 | BACKDRAFT - AZ |  | 2007-01-29 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-AR | GF-2616 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
|  | GF-2617 | 1 | 0
4 | 1303-AR | GF-2618 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1305-MD | GF-2618 | 1 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GF-2619 | 1 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1301-MD | GF-2621 | 1 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | - |  | AK | 2006-11-20 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-AR | GF-2621 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
2 | 1107-MD | GF-2621 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
1 | 1501-AR | GF-2623 | 1 | 0 |  | DR | 2007-03-07 | 2007-03-07 |  | 2007-03-07 |  | DG | 2007-03-07 | [23 empty] | 2007-03-30
2 | 1107-MD | GF-2624 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
|  | GF-2625 | 1 | 0
1 | 1501-AR | GF-2626 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
2 | 1107-MD | GF-2628 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
1 |  | GF-2629 | 1 | 0
1 | 1501-AR | GF-2630 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
4 | 1401-AR | GF-2631 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  |  |  |  | 2006-12-13
4 | 1401-AR | GF-2632 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  |  |  |  | 2006-12-13
4 | 1401-AR | GF-2633 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  |  |  |  | 2006-12-13
2 | 1107-MD | GF-2634 | 1 | 0 | NEW | JJL | 2006-12-14 | [17 empty] | 2006-12-14 | AK | HOLD W/ AK |  | HOLD W/ AK |  | 2007-01-04 | 2007-01-04 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1307-MD | GF-2634 | 1 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 |  |  | HT | 2007-02-08 | 2007-02-20 | [12 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1304-MD | GF-2635 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 |  |  | AK | 2006-12-13 | 2006-12-18 |  | 2007-01-24 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1304-AR | GF-9013 | 1 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1304-AR | GF-9013 | 2 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1304-AR | GF-9013 | 3 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1304-AR | GF-9013 | 4 | 0 | LINE DELETED | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02
4 | 1304-AR | GF-9013 | 5 | 0 | LINE DELETED | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02
4 | 1304-AR | GF-9013 | 6 | 0 | LINE DELETED | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02
4 | 1301-MD | GF-9019 | 1 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | 2006-11-20 | 2007-01-15 | AK | 2006-11-20 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-03-14
4 | 1301-MD | GF-9019 | 2 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | 2006-11-20 | 2007-01-15 | AK | 2006-11-20 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-03-14
4 | 1301-MD | GF-9019 | 3 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | 2006-11-20 | 2007-01-15 | AK | 2006-11-20 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1301-MD | GF-9019 | 4 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | - |  | AK | 2006-11-20 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1301-MD | GF-9019 | 5 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | - |  | AK | 2006-11-20 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
[8 empty] | 2006-11-20 | 2006-11-23 | 2006-11-20 | 2007-01-15 | AK | 2006-11-20 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A
4 | 1301-MD | GF-9019 | 7 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | - |  | AK | 2006-11-20 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1301-MD | GF-9019 | 8 | 0 |  | WAP | 2006-11-20 | 2006-11-20 | 2006-11-23 | - |  | AK | 2006-11-20 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-16 |  | 2007-01-16 | AK |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
|  | GF-9035 | 1 | 0
4 | 1401-MD | GP-3001 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | GP-3001 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | GP-3002 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | GP-3003 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | GP-3004 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | GP-3005 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | GP-3006 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1303-AR | GP-3007 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1305-MD | GP-3007 | 1 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | GP-3007 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15
[8 empty] | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A
4 | 1305-MD | GP-3008 | 2 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  | 2006-12-18 | 2007-01-15 | AK | 2006-12-18 |  | 2007-01-15 | 2007-01-26 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GP-3008 | 3 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  | 2006-12-18 | 2007-01-15 | AK | 2006-12-18 |  | 2007-01-15 | 2007-01-26 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GP-3008 | 5 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1303-AR | GP-3008 | 4 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 | 2007-02-27 | 2007-03-06 | AK | 2007-02-27 | 2007-03-01 | 2007-03-07 | [21 empty] | 2007-03-30
4 | 1303-AR | GP-3008 | 5 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
2 | 1101-AR | GP-3009 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
4 | 1303-MD | GP-3009 | 1 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | AK | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1307-MD | GP-3009 | 1 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 | 2007-02-08 | 2007-02-16 | HT | 2007-02-08 | 2007-02-20 | 2007-02-16 | [11 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-AR | GP-3010 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
[8 empty] | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | AK | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A
4 | 1401-AR | GP-3010 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | GP-3010 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | GP-3011 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | GP-3012 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | GP-3013 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1303-MD | GP-3014 | 1 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | AK | 2006-11-23 | 2006-11-27 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-AR | GP-3016 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1303-MD | GP-3016 | 1 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | AK | 2006-11-23 | 2006-11-27 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
2 | 1107-MD | GP-3016 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | GP-3017 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | GP-3018 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | GP-3019 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1305-MD | GP-3020 | 1 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1303-AR | GP-3021 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1305-MD | GP-3021 | 1 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
2 | 1107-MD | GP-3021 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
|  | GP-3024 | 1 | 0
4 | 1303-MD | GP-3025 | 1 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | AK | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | GP-3026 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | GP-3027 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GP-3028 | 1 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  | 2006-12-18 | 2007-01-15 | AK | 2006-12-18 |  | 2007-01-15 | 2007-01-26 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1303-AR | GP-3031 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1304-MD | GP-3031 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 |  |  | AK | 2006-12-13 | 2006-12-18 |  | 2007-01-24 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1401-AR | GP-3031 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | GP-3031 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
|  | GP-3032 | 1 | 0
|  | GP-3033 | 1 | 0
|  | GP-3034 | 1 | 0
2 | 1107-MD | GP-3035 | 1 | 0 | NEW | JJL | 2006-12-14 | [17 empty] | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1302-AR | GP-3036 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1303-MD | GP-3036 | 1 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | AK | 2006-11-23 | 2006-11-27 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
2 | 1107-MD | GP-3036 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | RO | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 | BACKDRAFT-JJL |  | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
4 | 1303-MD | GP-9007 | 1 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | AK | 2006-11-23 | 2006-11-27 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1303-MD | GP-9007 | 2 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | AK | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-04-10
4 | 1303-MD | GP-9007 | 3 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | AK | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-04-10
4 | 1303-MD | GP-9007 | 4 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | AK | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-04-10
4 | 1303-MD | GP-9007 | 5 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | AK | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-04-10
4 | 1303-MD | GP-9007 | 6 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | AK | 2006-11-23 | 2006-11-27 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1303-MD | GP-9007 | 7 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | AK | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1303-MD | GP-9007 | 8 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | AK | 2006-11-23 | 2006-11-27 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1303-MD | GP-9007 | 9 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | AK | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1303-MD | GP-9007 | 10 | 0 |  | WAP | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | AK | 2006-11-23 | 2006-11-27 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GP-9015 | 1 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GP-9015 | 2 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  | 2006-12-18 | 2007-01-15 | AK | 2006-12-18 |  | 2007-01-15 | 2007-01-26 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GP-9015 | 3 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  | 2006-12-18 | 2007-01-15 | AK | 2006-12-18 |  | 2007-01-15 | 2007-01-26 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GP-9015 | 4 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  | 2006-12-18 | 2007-01-15 | AK | 2006-12-18 |  | 2007-01-15 | 2007-01-26 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GP-9015 | 5 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  | 2006-12-18 | 2007-01-15 | AK | 2006-12-18 |  | 2007-01-15 | 2007-01-26 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GP-9015 | 6 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GP-9015 | 7 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  | 2006-12-18 | 2007-01-15 | AK | 2006-12-18 |  | 2007-01-15 | 2007-01-26 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GP-9015 | 8 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  |  |  | AK | 2006-12-18 |  |  | 2007-01-26 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1305-MD | GP-9015 | 9 | 0 |  | GM | 2006-12-18 | 2006-12-18 |  | 2006-12-18 | 2007-01-15 | AK | 2006-12-18 |  | 2007-01-15 | 2007-01-26 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-26 | 2007-02-08 |  | 2007-02-08 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
3 | 1701-AR | HG-3501 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-AR | HG-3502 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-AR | HG-3504 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-AR | HG-3507 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-AR | HG-3508 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | HG-3502 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-3503 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-3504 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-3505 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-3506 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 | 2007-01-12 | 2007-01-31 | WA | 2007-01-10 | 2007-01-16 | 2007-01-31 | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-3507 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 | 2007-01-12 | 2007-01-31 | WA | 2007-01-10 | 2007-01-16 | 2007-01-31 | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-3508 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 | 2007-01-12 | 2007-01-31 | WA | 2007-01-10 | 2007-01-16 | 2007-01-31 | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 1 |  | 2007-05-11 | 2007-05-11
3 | 1701-MD | HG-3509 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-3510 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 | 2007-01-12 | 2007-01-31 | WA | 2007-01-10 | 2007-01-16 | 2007-01-31 | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | [5 empty] | 2007-03-14 | 1 |  | 2007-05-11 | 2007-05-11
3 | 1701-MD | HG-3511 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
4 | 1401-AR | HG-3512 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15
|  | HG-3514 | 1 | 0 | CHECK W/ IAN-NOT ON FINAL 1401-AR |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15
|  | HG-3515 | 1 | 0 | CHECK W/ IAN-NOT ON FINAL 1401-AR |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15
4 | 1401-MD | HG-3516 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | HG-3517 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | HG-3518 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1402-AR | HG-3518 | 1 | 0 |  | RO
4 | 1402-AR | HG-3518 | 2 | 0 |  | RO
4 | 1402-AR | HG-3519 | 1 | 0 |  | RO
3 | 1701-AR | HG-3518 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | HG-3518 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
4 | 1401-MD | HG-3518 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1402-MD | HG-3518 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 | 2007-01-19 | 2007-01-31 | WAP | 2007-01-19 | 2007-01-26 | 2007-01-31 | 2007-02-05 | 2007-02-20 | 2007-01-31 |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-03-14
4 | 1402-MD | HG-3519 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 | 2007-01-19 | 2007-01-31 | WAP | 2007-01-19 | 2007-01-26 | 2007-01-31 | 2007-02-05 | 2007-02-20 | 2007-01-31 |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1401-MD | HG-3520 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | HG-3521 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
3 | 1701-MD | HG-3524 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-3525 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-AR | HG-3526 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | HG-3526 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-3527 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-AR | HG-3528 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | HG-3528 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-AR | HG-3529 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | HG-3529 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-3529 | 2 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 | 2007-01-12 | 2007-01-31 | WA | 2007-01-10 | 2007-01-16 | 2007-01-31 | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
|  | HG-3530 | 1 | 0
1 | 1503-AR | HG-3531 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1601-MD | HG-3531 | 1 | 0 | WAS HG-3532-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3531 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | HG-3531 | 2 | 0 | WAS HG-3532-03 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | HG-3531 | 3 | 0 | WAS HG-3532-04 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 |  | HG-3532 | 1 | 0
|  | HG-3532 | 1 | 0
1 | 1601-MD | HG-3533 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 |  |  |  | 2006-11-09 |  |  |  | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13 | 1 | BACKDRAFT-JJL 11/1/7 | 2007-01-15 | 2007-01-15
1 |  | HG-3534 | 1 | 0
1 | 1601-AR | HG-3534 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | HG-3534 | 1 | 0 | WAS HG-3534-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | HG-3534 | 2 | 0 | WAS HG-3534-03 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | HG-3534 | 3 | 0 | WAS HG-3534-04 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1503-AR | HG-3535 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1601-AR | HG-3536 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | HG-3536 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 |  | HG-3537 | 1 | 0
1 | 1601-AR | HG-3537 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | HG-3537 | 1 | 0 | WAS HG-3537-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3537 | 2 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | HG-3537 | 2 | 0 | WAS HG-3537-03 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | HG-3537 | 3 | 0 | WAS HG-3537-04 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
3 | 1701-AR | HG-3539 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-AR | HG-3541 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-AR | HG-3542 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | HG-3542 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 | 2007-01-12 | 2007-01-31 | WA | 2007-01-10 | 2007-01-16 | 2007-01-31 | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | [5 empty] | 2007-03-14
3 | 1701-AR | HG-3543 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-AR | HG-3544 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | HG-3544 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 | 2007-01-12 | 2007-01-31 | WA | 2007-01-10 | 2007-01-16 | 2007-01-31 | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-25 |  | 2007-01-25 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
4 | 1302-AR | HG-3545 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1302-MD | HG-3545 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | AK | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1302-AR | HG-3546 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-20 | 2007-02-22 |  |  | AK | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
4 | 1302-MD | HG-3546 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | AK | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-04-10
|  | HG-3548 | 1 | 0
|  | HG-3552 | 1 | 0
1 | 1601-AR | HG-3561 | 1 | 0 |  | JJL | [30 empty] | 2007-03-30
1 | 1601-AR | HG-3562 | 1 | 0 |  | JJL | [30 empty] | 2007-03-30
1 | 1601-AR | HG-3563 | 1 | 0 |  | JJL | [30 empty] | 2007-03-30
1 | 1601-AR | HG-3564 | 1 | 0 |  | JJL | [30 empty] | 2007-03-30
1 | 1601-MD | HG-3580 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3580 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | HG-3581 | 1 | 0 | WAS HG-3581-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3581 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-31 | 2007-02-06 | DG | 2007-01-18 | 2007-01-22 | 2007-02-06 | [21 empty] | 2007-03-30
1 | 1601-MD | HG-3582 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3582 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | HG-3583 | 1 | 0 | WAS HG-3583-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3583 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-31 | 2007-02-06 | DG | 2007-01-18 | 2007-01-22 | 2007-02-06 | [21 empty] | 2007-03-30
1 | 1601-MD | HG-3584 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3584 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | HG-3585 | 1 | 0 | WAS HG-3585-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3585 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-31 | 2007-02-06 | DG | 2007-01-18 | 2007-01-22 | 2007-02-06 | [21 empty] | 2007-03-30
1 | 1601-AR | HG-3586 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | HG-3586 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3587 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-31 | 2007-02-06 | DG | 2007-01-18 | 2007-01-22 | 2007-02-06 | [21 empty] | 2007-03-30
1 | 1601-MD | HG-3587 | 1 | 0 | WAS HG-3587-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1503-AR | HG-3588 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | HG-3589 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  | 2007-02-14 | 2007-02-20 | DG | 2007-02-14 |  | 2007-02-20 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | HG-3590 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | HG-3591 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | HG-3592 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | HG-3593 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  | 2007-02-14 | 2007-02-20 | DG | 2007-02-14 |  | 2007-02-20 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | HG-3594 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | HG-3595 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | HG-3596 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | HG-3597 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  | 2007-02-14 | 2007-02-20 | DG | 2007-02-14 |  | 2007-02-20 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | HG-3598 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | HG-3599 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | HG-3600 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | HG-3601 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  | 2007-02-14 | 2007-02-20 | DG | 2007-02-14 |  | 2007-02-20 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | HG-3602 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | HG-3603 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | HG-3604 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | HG-3605 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  | 2007-02-14 | 2007-02-20 | DG | 2007-02-14 |  | 2007-02-20 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | HG-3606 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | HG-3607 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | HG-3608 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | HG-3609 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  | 2007-02-14 | 2007-02-20 | DG | 2007-02-14 |  | 2007-02-20 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | HG-3610 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | HG-3611 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1601-MD | HG-3612 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | HG-3613 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
4 | 2101-AR | HG-3614 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | HG-3615 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-AR | HG-3616 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | HG-3617 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-AR | HG-3618 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | HG-3619 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-AR | HG-3620 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | HG-3621 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
3 | 1201-AR | HG-3622 | 1 | 0 |  | WA | [30 empty] | 2007-03-30
|  | HG-3622 | 1 | 0 | CHECK W/ HT-NOT ON FINAL 2101-AR | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-MD | HG-3622 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | DG | 2006-11-23 | 2007-01-27 |  | 2007-02-13 | 2007-02-14 |  |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
|  | HG-3624 | 1 | 0
|  | HG-3625 | 1 | 0
|  | HG-3626 | 1 | 0
|  | HG-3630 | 1 | 0
|  | HG-3631 | 1 | 0
3 | 1201-AR | HG-3634 | 1 | 0 |  | WA | [30 empty] | 2007-03-30
|  | HG-3634 | 1 | 0 | CHECK W/ HT-NOT ON FINAL 2101-AR | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-MD | HG-3634 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | DG | 2006-11-23 | 2007-01-27 |  | 2007-02-13 | 2007-02-14 |  |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
3 | 1801-MD | HG-3640 | 1 | 0 | deleted |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | line deleted
3 | 1801-MD | HG-3641 | 1 | 0 | deleted |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | line deleted
4 | 1402-AR | HG-3648 | 1 | 0 |  | RO
4 | 1402-AR | HG-3649 | 1 | 0 |  | RO
4 | 1402-AR | HG-3650 | 1 | 0 |  | RO
4 | 1402-AR | HG-3651 | 1 | 0 |  | RO
4 | 1402-AR | HG-3652 | 1 | 0 |  | RO
4 | 1402-AR | HG-3653 | 1 | 0 |  | RO
4 | 1402-AR | HG-3656 | 1 | 0 |  | RO
4 | 1402-AR | HG-3656 | 2 | 0 |  | RO
|  | HG-3655 | 1 | 0
4 | 1402-AR | IA-4016 | 1 | 0 |  | RO
4 | 1402-AR | HG-3665 | 1 | 0 |  | RO
4 | 1402-AR | HG-3665 | 2 | 0 |  | RO
[8 empty] | 2007-01-19 | 2007-01-25 |  |  | WAP | 2007-01-19 | 2007-01-26 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A
4 | 1402-MD | HG-3665 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 |  |  | WAP | 2007-01-19 | 2007-01-26 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1402-AR | HG-3666 | 1 | 0 |  | RO
4 | 1302-MD | HG-3667 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | 2006-11-21 | 2007-01-15 | AK | 2006-11-21 | 2006-11-24 | 2007-01-15 | 2007-01-08 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
1 | 1601-MD | HG-3670 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 |  |  |  | 2006-11-09 |  |  |  | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13 | 1 | BACKDRAFT-JJL 11/1/7 | 2007-01-15 | 2007-01-15
3 | 1701-AR | HG-3671 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-AR | HG-3672 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | HG-3673 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-19 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-19 | 2007-01-25 |  | 2007-01-25 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-AR | HG-3674 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | HG-3674 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-19 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-19 | 2007-01-25 |  | 2007-01-25 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
1 | 1601-AR | HG-3675 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | HG-3676 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | HG-3677 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | HG-3678 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | HG-3679 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | HG-3680 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | HG-3681 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | HG-3682 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
|  | HG-3683 | 1 | 0
1 | 1503-AR | HG-3684 | 1 | 0 |  | DR | 2007-02-23 | 2007-03-02 |  |  |  | DG | 2007-02-23 | [23 empty] | 2007-03-30
4 | 1302-MD | HG-3685 | 1 | 0 |  | WAP | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | AK | 2006-11-21 | 2006-11-24 |  | 2007-01-08 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-08 | 2007-01-24 |  | 2007-01-24 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
|  | HG-3686 | 1 | 0 | CHECK W/ IAN-NOT ON FINAL 1701-AR | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22
3 | 1701-MD | HG-3686 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
2 | 1101-AR | HG-3687 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
4 | 1303-AR | HG-3687 | 1 | 0 |  | GM | [30 empty] | 2007-03-30
4 | 1304-MD | HG-3687 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 | 2006-12-15 | 2007-01-15 | AK | 2006-12-13 | 2006-12-18 | 2007-01-15 | 2007-01-24 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-04-10
2 | 1101-AR | HG-3688 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
4 | 1303-AR | HG-3688 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
4 | 1304-MD | HG-3688 | 1 | 0 |  | GM | 2006-12-13 | 2006-12-13 | 2006-12-18 |  |  | AK | 2006-12-13 | 2006-12-18 |  | 2007-01-24 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-01-24 | 2007-02-01 |  | 2007-02-01 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
|  | HG-3691 | 1 | 0
|  | HG-3692 | 1 | 0
|  | HG-3693 | 1 | 0
4 | 2101-AR | HG-3696 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | HG-3697 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
1 | 1601-AR | HG-3698 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | HG-3698 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3699 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-31 | 2007-02-06 | DG | 2007-01-18 | 2007-01-22 | 2007-02-06 | [21 empty] | 2007-03-30
1 | 1601-MD | HG-3699 | 1 | 0 | WAS HG-3699-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3700 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-AR | HG-3701 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1501-AR | HG-3702 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | HG-3703 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  | 2007-02-14 | 2007-02-20 | DG | 2007-02-14 |  | 2007-02-20 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | HG-3704 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | HG-3705 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
3 | 1701-MD | HG-3706 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-AR | HG-3707 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
1 | 1601-AR | HG-3708 | 1 | 0 |  | JJL | [30 empty] | 2007-03-30
1 | 1601-AR | HG-3709 | 1 | 0 |  | JJL | [30 empty] | 2007-03-30
4 | 1402-AR | HG-3710 | 1 | 0 |  | RO
4 | 1402-AR | HG-3710 | 2 | 0 |  | RO
4 | 1402-MD | HG-3710 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 |  |  | WAP | 2007-01-19 | 2007-01-26 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
1 | 1501-AR | HG-3711 | 1 | 0 |  | DR | 2007-03-12 | 2007-03-12 |  | 2007-03-14 |  | DG | 2007-03-12 | [23 empty] | 2007-03-30
1 | 1501-AR | HG-3712 | 1 | 0 |  | DR | 2007-03-12 | 2007-03-12 |  |  |  | DG | 2007-03-12 | [23 empty] | 2007-03-30
3 | 1701-MD | HG-3713 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1201-AR | HG-3714 | 1 | 0 |  | WA | 2007-02-08 | 2007-02-08 | 2007-02-16 |  |  | W/ KY | 2007-02-20 | 2007-02-16 | [22 empty] | 2007-03-30
3 | 1201-AR | HG-3715 | 1 | 0 |  | WA | 2007-02-08 | 2007-02-08 | 2007-02-16 |  |  | W/ KY | 2007-02-20 | 2007-02-16 | [22 empty] | 2007-03-30
3 | 1801-AR | HG-3716 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1801-AR | HG-3717 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1201-AR | HG-3719 | 1 | 0 |  | WA | 2007-02-08 | 2007-02-08 | 2007-02-16 |  |  | W/ KY | 2007-02-20 | 2007-02-16 | [22 empty] | 2007-03-30
4 | 2101-AR | HG-3720 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | HG-3720 | 2 | 0 |  | AZ | 2007-02-23
4 | 2101-AR | HG-3721 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
3 | 1201-AR | HG-3722 | 1 | 0 |  | WA | 2007-02-08 | 2007-02-08 | 2007-02-16 |  |  | W/ KY | 2007-02-20 | 2007-02-16 | [22 empty] | 2007-03-30
4 | 1401-AR | HG-3723 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | HG-3723 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | HG-3723 | 2 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | HG-3724 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | HG-3724 | 1 | 0 | LINE DELETED |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | LINE DELETED | [10 empty] | LINE DELETED | [10 empty] | 2007-02-28
4 | 1307-MD | HG-3725 | 1 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 |  |  | HT | 2007-02-08 | 2007-02-20 | [12 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
[8 empty] | 2007-02-08 | 2007-02-20 |  |  | HT | 2007-02-08 | 2007-02-20 | [12 empty] | 2007-02-21 | A
4 | 1307-MD | HG-3725 | 3 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 |  |  | HT | 2007-02-08 | 2007-02-20 | [12 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1307-MD | HG-3726 | 1 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 |  |  | HT | 2007-02-08 | 2007-02-20 | [12 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1307-MD | HG-3726 | 2 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 |  |  | HT | 2007-02-08 | 2007-02-20 | [12 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
2 | 1101-AR | HG-3727 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
2 | 1107-MD | HG-3727 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1107-MD | HG-3728 | 1 | 0 |  | JJL | 2006-11-21 | 2006-11-21 | 2006-11-23 | - |  | RO | 2006-11-21 | 2006-11-24 |  | 2006-11-30 | 2006-11-27 |  |  | BACKDRAFT-JJL | 2006-11-30 |  | 2006-12-14 |  | 2006-12-14 | AK | 2006-12-20 |  | 2006-12-20 | 2006-12-20 | 2007-01-04 | 2007-01-04 | 2007-01-09 |  |  |  | 2007-01-10 | 2007-01-11 | 2007-01-11 | [5 empty] | 2007-01-26
2 | 1101-AR | HG-3729 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
2 | 1101-AR | HG-3730 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
4 | 1403-AR | HG-3733 | 1 | 0
4 | 1403-AR | HG-3734 | 1 | 0
4 | 1403-MD | HG-3733 | 1 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | HG-3733 | 2 | 0 | NEW | [27 empty] | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | HG-3734 | 1 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
2 | 1101-AR | HG-3735 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
2 | 1101-AR | HG-3736 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
2 | 1101-AR | HG-3737 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
2 | 1101-AR | HG-3738 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
2 | 1101-AR | HG-3739 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
1 | 1601-MD | HG-3740 | 1 | 0 |  | JJL | [34 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3740 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | HG-3741 | 1 | 0 |  | JJL | [34 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | HG-3741 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
2 | 1101-AR | HG-3742 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
2 | 1101-AR | HG-3743 | 1 | 0 |  | JL | [30 empty] | 2007-03-30
3 | 1701-AR | HG-9021 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 | 2007-02-07 | 2007-02-21 | W/ KY | 2007-02-20 | 2007-02-22 | 2007-02-21 | [21 empty] | 2007-03-30
3 | 1701-AR | HG-9021 | 2 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 | 2007-02-07 | 2007-02-21 | W/ KY | 2007-02-20 | 2007-02-22 | 2007-02-21 | [21 empty] | 2007-03-30
3 | 1701-AR | HG-9023 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-AR | HG-9023 | 2 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 | 2007-02-07 | 2007-02-21 | W/ KY | 2007-02-20 | 2007-02-22 | 2007-02-21 | [21 empty] | 2007-03-30
3 | 1701-AR | HG-9023 | 3 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 | 2007-02-07 | 2007-02-21 | W/ KY | 2007-02-20 | 2007-02-22 | 2007-02-21 | [21 empty] | 2007-03-30
3 | 1701-AR | HG-9023 | 4 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 | 2007-02-07 | 2007-02-21 | W/ KY | 2007-02-20 | 2007-02-22 | 2007-02-21 | [21 empty] | 2007-03-30
3 | 1701-AR | HG-9023 | 5 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 | 2007-02-07 | 2007-02-21 | W/ KY | 2007-02-20 | 2007-02-22 | 2007-02-21 | [21 empty] | 2007-03-30
3 | 1701-AR | HG-9023 | 6 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | HG-9024 | 1 | 0 |  | AZ | 2007-01-15 | 2007-01-15 | 2007-01-16 |  |  | WA | 2007-01-15 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-9024 | 2 | 0 |  | AZ | 2007-01-15 | 2007-01-15 | 2007-01-16 |  |  | WA | 2007-01-15 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-9024 | 3 | 0 |  | AZ | 2007-01-15 | 2007-01-15 | 2007-01-16 |  |  | WA | 2007-01-15 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-9024 | 4 | 0 | NEW | AZ | 2007-01-25 |  |  |  |  | WA | 2007-01-25 | [9 empty] | 2007-01-24 |  | 2007-01-24 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1701-MD | HG-9025 | 1 | 0 |  | AZ | 2007-01-15 | 2007-01-15 | 2007-01-16 |  |  | WA | 2007-01-15 | 2007-01-16 |  | 2007-01-17 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-17 | 2007-01-25 |  | 2007-01-25 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
|  | HG-9034 | 1 | 0
3 | 1701-AR | HG-9045 | 1 | 0 | [32 empty] | 2007-03-30
3 | 1701-AR | HG-9045 | 2 | 0 | [32 empty] | 2007-03-30
1 | 1601-AR | IA-4006 | 1 | 0 |  | JJL | [30 empty] | 2007-03-30
1 | 1503-AR | IA-4006 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | IA-4007 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  | 2007-02-15 | 2007-02-21 | DG | 2007-02-15 |  | 2007-02-21 | [21 empty] | 2007-03-30
1 | 1503-AR | IA-4008 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | IA-4009 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | IA-4010 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1601-AR | IA-4011 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | IA-4011 | 1 | 0 | WAS IA-4011-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1503-AR | IA-4012 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
|  | IA-4013 | 1 | 0
|  | IA-4014 | 1 | 0
4 | 1302-AR | IA-4015 | 1 | 0 |  | GM | 2007-02-20 | 2007-03-30 | [28 empty] | 2007-03-30
4 | 1303-AR | IA-4015 | 1 | 0 |  | GM |  | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1402-MD | IA-4016 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 |  |  | WAP | 2007-01-19 | 2007-01-26 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
|  | IA-4017 | 1 | 0
3 | 1701-AR | IA-4018 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | IA-4018 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-19 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-19 | 2007-01-25 |  | 2007-01-25 | WA | 2007-01-26 | BACDRAFT - AZ |  | 2007-01-26 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1801-MD | IA-4019 | 1 | 0 | deleted |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | line deleted
3 | 1201-AR | IA-4020 | 1 | 0 |  | WA | [30 empty] | 2007-03-30
|  | IA-4020 | 1 | 0 | CHECK W/ HT-NOT ON FINAL 2101-AR | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-MD | IA-4020 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | DG | 2006-11-23 | 2007-01-27 |  | 2007-02-13 | 2007-02-14 |  |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
1 | 1503-AR | IA-4022 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
1 | 1503-AR | IA-4023 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
1 | 1502-AR | IA-4024 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
1 | 1502-AR | IA-4025 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
1 | 1502-AR | IA-4026 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
1 | 1501-AR | IA-4027 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
1 | 1501-AR | IA-4028 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
4 | 1401-AR | IA-4029 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | IA-4029 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | IA-4030 | 1 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
1 | 1503-AR | IA-4031 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
4 | 1403-AR | IA-4030 | 1 | 0
1 | 1503-AR | IA-9020 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
|  | LC-4501 | 1 | 0
4 | 1401-MD | LC-4503 | 1 | 0 | NEW |  | 2007-01-30 |  |  |  |  | WAP |  |  |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | LC-4506 | 1 | 0 | NEW |  | 2007-01-30 |  |  |  |  | WAP |  |  |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1402-MD | LC-4507 | 1 | 0 | NEW | RO | 2007-02-07 |  |  |  |  | WAP |  |  |  |  | 2007-02-20 | [5 empty] | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1402-MD | LC-4508 | 1 | 0 | NEW | RO | 2007-02-07 |  |  |  |  | WAP |  |  |  |  | 2007-02-20 | [5 empty] | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
1 | 1601-MD | LC-4510 | 1 | 0 | [36 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
|  | LC-4512 | 1 | 0
|  | LC-4513 | 1 | 0
|  | LC-4519 | 1 | 0
4 | 1401-MD | LC-4520 | 1 | 0 | NEW |  | 2007-01-30 |  |  |  |  | WAP |  |  |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
|  | LC-9011 | 1 | 0
4 | 1307-MD | LH-5001 | 1 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 |  |  | HT | 2007-02-08 | 2007-02-20 | [12 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | LH-5001 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | LH-5001 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-MD | LH-5001 | 2 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | LH-5002 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
[8 empty] | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A
|  | LH-5002 | 2 | 0 | CHECK W/ IAN-NOT ON FINAL 1401-AR |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-AR | LH-5003 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1402-AR | LH-5003 | 1 | 0 |  | RO
4 | 1405-MD | LH-5003 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 |  | 2007-01-29 | 2007-01-29 |  |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1405-MD | LH-5004 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 |  | 2007-01-29 | 2007-01-29 |  |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1405-MD | LH-5005 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | 2007-01-29 | 2007-01-29 | 2007-02-20 |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1402-AR | LH-5006 | 1 | 0 |  | RO
4 | 1402-AR | LH-5007 | 1 | 0 |  | RO
4 | 1405-MD | LH-5007 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | 2007-01-29 | 2007-01-29 | 2007-02-20 |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1405-MD | LH-5008 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 |  | 2007-01-29 | 2007-01-29 |  |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1405-MD | LH-5009 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | 2007-01-29 | 2007-01-29 | 2007-02-20 |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1402-AR | LH-5010 | 1 | 0 |  | RO
4 | 1402-AR | LH-5011 | 1 | 0 |  | RO
4 | 1405-MD | LH-5011 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | 2007-01-29 | 2007-01-29 | 2007-02-20 |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1405-MD | LH-5012 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 |  | 2007-01-29 | 2007-01-29 |  |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1405-MD | LH-5013 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | 2007-01-29 | 2007-01-29 | 2007-02-20 |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1402-AR | LH-5014 | 1 | 0 |  | RO
4 | 1405-MD | LH-5015 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | 2007-01-29 | 2007-01-29 | 2007-02-20 |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1402-AR | LH-5015 | 1 | 0 |  | RO
4 | 1402-AR | LH-5016 | 1 | 0 |  | RO
4 | 1403-AR | LH-5016 | 1 | 0
[8 empty] | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A
4 | 1405-MD | LH-5016 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 |  | 2007-01-29 | 2007-01-29 |  |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1403-AR | LH-5018 | 1 | 0
[8 empty] | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A
3 | 1201-AR | LH-5019 | 1 | 0 |  | WA | 2007-02-08 | 2007-02-08 | 2007-02-16 |  |  | W/ KY | 2007-02-20 | 2007-02-16 | [22 empty] | 2007-03-30
4 | 1401-AR | LH-5020 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | LH-5020 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15 | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | LH-5024 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1402-AR | LH-5024 | 1 | 0 |  | RO
4 | 1402-AR | LH-5025 | 1 | 0 |  | RO
4 | 1402-MD | LH-5025 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 | 2007-01-19 | 2007-01-31 | WAP | 2007-01-19 | 2007-01-26 | 2007-01-31 | 2007-02-05 | 2007-02-20 | 2007-01-31 |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1401-AR | LH-5026 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | LH-5026 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1402-AR | LH-5026 | 1 | 0 |  | RO
4 | 1402-MD | LH-5026 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 |  |  | WAP | 2007-01-19 | 2007-01-26 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1306-MD | LH-5027 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1306-MD | LH-5027 | 2 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 | 2006-12-21 | 2007-01-29 | AK | 2006-12-21 | 2007-01-02 | 2007-01-29 | 2007-02-05 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-13 |  | 2007-02-13 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-03-14
4 | 1306-MD | LH-5028 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 | 2006-12-21 | 2007-01-29 | AK | 2006-12-21 | 2007-01-02 | 2007-01-29 | 2007-02-05 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1304-AR | LH-5027 | 1 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1304-AR | LH-5028 | 1 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1303-AR | LH-5029 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1306-MD | LH-5029 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 | 2006-12-21 | 2007-01-29 | AK | 2006-12-21 | 2007-01-02 | 2007-01-29 | 2007-02-05 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1401-AR | LH-5029 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | LH-5029 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1306-MD | LH-5029 | 2 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1303-AR | LH-5030 | 1 | 0 |  | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1306-MD | LH-5030 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 | 2006-12-21 | 2007-01-29 | AK | 2006-12-21 | 2007-01-02 | 2007-01-29 | 2007-02-05 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-03-14
4 | 1401-AR | LH-5030 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-MD | LH-5030 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1306-MD | LH-5030 | 2 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 |  |  | AK | 2006-12-21 | 2007-01-02 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1304-AR | LH-5031 | 1 | 0 |  | GM | 2007-03-02 | 2007-03-02 |  |  |  | AK | 2007-03-02 | [23 empty] | 2007-03-30
4 | 1306-MD | LH-5032 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 | 2006-12-21 | 2007-01-29 | AK | 2006-12-21 | 2007-01-02 | 2007-01-29 | 2007-02-05 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1306-MD | LH-5033 | 1 | 0 |  | GM | 2006-12-21 | 2007-01-02 | 2007-01-02 | 2006-12-21 | 2007-01-29 | AK | 2006-12-21 | 2007-01-02 | 2007-01-29 | 2007-02-05 | 2007-02-20 | 2007-02-20 |  | BACKDRAFT-GM |  | 2007-02-05 | 2007-02-12 |  | 2007-02-12 | AK | 2007-02-20 | A | [9 empty] | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
3 | 1801-MD | LH-5034 | 1 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | [5 empty] | 2007-03-14
3 | 1801-AR | LH-5035 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1801-MD | LH-5035 | 1 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | [5 empty] | 2007-03-14
3 | 1801-AR | LH-5036 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1801-MD | LH-5036 | 1 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
|  | LH-5037 | 1 | 0
3 | 1801-MD | LH-5038 | 1 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
4 | 1405-MD | LH-5039 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | 2007-01-29 | 2007-01-29 | 2007-02-20 |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1405-MD | LH-5040 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | 2007-01-29 | 2007-01-29 | 2007-02-20 |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1405-MD | LH-5041 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | 2007-01-29 | 2007-01-29 | 2007-02-20 |  | BACKDRAFT-RO | 2007-01-29 |  | 2007-02-05 |  | 2007-02-05 | WAP |  |  |  |  | 2007-02-13 | 2007-02-13 | 2007-02-13 | A |  |  |  | 2007-02-21 | 2007-02-13 | [5 empty] | 2007-02-28
4 | 1404-MD | LH-5044 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1404-MD | LH-5045 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1401-AR | LH-5046 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1402-AR | LH-5046 | 1 | 0 |  | RO
4 | 1402-AR | LH-5047 | 1 | 0 |  | RO
4 | 1402-AR | LH-5048 | 1 | 0 |  | RO
4 | 1402-AR | LH-5049 | 1 | 0 |  | RO
4 | 1401-AR | LH-5047 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-AR | LH-5048 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-AR | LH-5049 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1404-MD | LH-5050 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-03-14
4 | 1404-MD | LH-5051 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | LH-5050 | 1 | 0 | NEW | [27 empty] | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | LH-5051 | 1 | 0 | NEW | [27 empty] | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | LH-5052 | 1 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1404-MD | LH-5052 | 1 | 0 | NEW | [27 empty] | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | LH-5053 | 1 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1404-MD | LH-5053 | 1 | 0 | NEW | [27 empty] | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | LH-5054 | 1 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | LH-5054 | 2 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | LH-5055 | 1 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
[8 empty] | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A
[8 empty] | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A
4 | 1402-AR | LH-9003 | 1 | 0 |  | RO
4 | 1402-AR | LH-9004 | 1 | 0 |  | RO
4 | 1401-AR | LH-9005 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15
4 | 1401-AR | LH-9005 | 2 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15
4 | 1401-AR | LH-9005 | 3 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15
4 | 1401-AR | LH-9005 | 4 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15
4 | 1401-AR | LH-9005 | 5 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-AR | LH-9005 | 6 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | WAP | 2006-11-23 | 2006-11-27 | 2007-01-15
4 | 1401-AR | LH-9005 | 7 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1401-AR | LH-9005 | 8 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
4 | 1402-AR | LH-9008 | 1 | 0 |  | RO
|  | LH-9017 | 1 | 0
|  | LH-9018 | 1 | 0
|  | LH-9041 | 1 | 0
|  | LH-9043 | 1 | 0
1 | 1503-AR | SB-5501 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | SB-5501 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | SB-5502 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | SB-5502 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SB-5503 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SB-5503 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SB-5504 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SB-5504 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SB-5505 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SB-5505 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | SB-5506 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | SB-5506 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
|  | SB-5507 | 1 | 0
4 | 2101-AR | SB-5508 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | SB-5509 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | SB-5509 | 2 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
1 | 1503-AR | SB-5511 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | SB-5512 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SB-5513 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SB-5514 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SB-5515 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | SB-5516 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | SB-5522 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1503-AR | SB-5523 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1503-AR | SB-5524 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1503-AR | SB-5525 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1503-AR | SB-5526 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1503-AR | SB-5527 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1502-AR | SB-5528 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1502-AR | SB-5529 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1502-AR | SB-5530 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1502-AR | SB-5531 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1502-AR | SB-5532 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1502-AR | SB-5533 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1502-AR | SB-5534 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1502-AR | SB-5535 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1502-AR | SB-5536 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1501-AR | SB-5537 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1501-AR | SB-5538 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1501-AR | SB-5539 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
|  | SB-5540 | 1 | 0
4 | 1307-MD | SB-5541 | 1 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 |  |  | HT | 2007-02-08 | 2007-02-20 | [12 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
1 | 1501-AR | SB-5542 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1501-AR | SB-5543 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1501-AR | SB-5544 | 1 | 0 |  | DR | 2007-01-11 | 2007-03-02 |  |  |  | DG | 2007-01-11 | [23 empty] | 2007-03-30
1 | 1501-AR | SB-5545 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | SB-5545 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | SB-5546 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | SB-5547 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | SB-5548 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SB-5549 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SB-5550 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SB-5551 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | SB-5552 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | SB-5553 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | SB-5554 | 1 | 0 |  | DR | 2007-02-23 | 2007-03-02 |  |  |  | DG | 2007-02-23 | [23 empty] | 2007-03-30
1 | 1503-AR | SB-5555 | 1 | 0 |  | DR | 2007-02-23 | 2007-03-02 |  |  |  | DG | 2007-02-23 | [23 empty] | 2007-03-30
1 | 1502-AR | SB-5556 | 1 | 0 |  | DR | 2007-02-23 | 2007-03-02 |  |  |  | DG | 2007-02-23 | [23 empty] | 2007-03-30
1 | 1502-AR | SB-5557 | 1 | 0 |  | DR | 2007-02-23 | 2007-03-02 |  |  |  | DG | 2007-02-23 | [23 empty] | 2007-03-30
1 | 1502-AR | SB-5558 | 1 | 0 |  | DR | 2007-02-23 | 2007-03-02 |  |  |  | DG | 2007-02-23 | [23 empty] | 2007-03-30
1 | 1501-AR | SB-5559 | 1 | 0 |  | DR | 2007-02-23 | 2007-03-02 |  |  |  | DG | 2007-02-23 | [23 empty] | 2007-03-30
1 | 1501-AR | SB-5560 | 1 | 0 |  | DR | 2007-02-23 | 2007-03-02 |  |  |  | DG | 2007-02-23 | [23 empty] | 2007-03-30
|  | SB-5561 | 1 | 0
|  | SB-5562 | 1 | 0
|  | SB-5563 | 1 | 0
|  | SB-5564 | 1 | 0
|  | SB-5565 | 1 | 0
|  | SB-5566 | 1 | 0
|  | SB-5567 | 1 | 0
|  | SB-5568 | 1 | 0
|  | SB-5569 | 1 | 0
|  | SB-5570 | 1 | 0
|  | SB-5571 | 1 | 0
|  | SB-5572 | 1 | 0
|  | SB-5573 | 1 | 0
|  | SB-5574 | 1 | 0
|  | SB-5575 | 1 | 0
|  | SB-5576 | 1 | 0
|  | SB-5577 | 1 | 0
|  | SB-5578 | 1 | 0
|  | SB-5579 | 1 | 0
|  | SB-5580 | 1 | 0
|  | SB-5581 | 1 | 0
1 | 1503-AR | SH-6001 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  | 2007-02-14 | 2007-02-20 | DG | 2006-12-18 |  | 2007-02-20 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | SH-6001 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | SH-6002 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  | 2006-12-18 | 2007-01-15 | DG | 2006-12-18 |  | 2007-01-15 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | SH-6002 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SH-6003 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  | 2006-12-18 | 2007-01-15 | DG | 2006-12-18 |  | 2007-01-15 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SH-6003 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SH-6004 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  | 2006-12-18 | 2007-01-15 | DG | 2006-12-18 |  | 2007-01-15 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SH-6004 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SH-6005 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  | 2006-12-18 | 2007-01-15 | DG | 2006-12-18 |  | 2007-01-15 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | SH-6005 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | SH-6006 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  | 2006-12-18 | 2007-01-15 | DG | 2006-12-18 |  | 2007-01-15 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | SH-6006 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
|  | SH-6007 | 1 | 0
|  | SH-6008 | 1 | 0
4 | 1307-MD | SH-6009 | 1 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 | 2007-02-08 | 2007-02-16 | HT | 2007-02-08 | 2007-02-20 | 2007-02-16 | [11 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
[8 empty] | 2007-02-08 | 2007-02-20 |  |  | HT | 2007-02-08 | 2007-02-20 | [12 empty] | 2007-02-21 | A
1 | 1501-AR | SH-6016 | 1 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  | 2006-12-18 | 2007-01-15 | DG | 2006-12-18 |  | 2007-01-15 | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | SH-6016 | 2 | 0 |  | DR | 2006-12-18 | 2007-03-02 |  |  |  | DG | 2006-12-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | UA-6503 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1601-AR | UA-6503 | 1 | 0 |  | JJL | [30 empty] | 2007-03-30
|  | UA-6504 | 1 | 0
1 | 1503-AR | UA-6505 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
1 | 1503-AR | UA-6506 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
1 | 1502-AR | UA-6507 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
1 | 1502-AR | UA-6508 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
1 | 1502-AR | UA-6509 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
1 | 1501-AR | UA-6510 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
1 | 1503-AR | UA-6511 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1601-AR | UA-6512 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | UA-6512 | 2 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13 | 1 | BACKDRAFT-JJL 11/1/7 | 2007-01-15 | 2007-01-15
1 | 1503-AR | UA-6513 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
|  | UA-6514 | 1 | 0
|  | UA-6515 | 1 | 0
1 | 1601-AR | UA-6516 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | UA-6516 | 1 | 0 | WAS UA-6524 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13 | 1 | BACKDRAFT-JJL 11/1/7 | 2007-01-15 | 2007-01-15
1 | 1503-AR | UA-6517 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | UA-6518 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | UA-6519 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | UA-6520 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
4 | 1302-AR | UA-6521 | 1 | 0 | NEW | GM | 2007-02-27 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
4 | 1402-AR | UA-6522 | 1 | 0 |  | RO
4 | 1403-MD | UA-6532 | 1 | 0 | WAS UA-6522; NEW | RO | 2007-02-14 | 2007-02-14 | 2007-02-20 |  |  |  |  | 2007-02-20 | [10 empty] | 2007-02-14 | DG |  | BACKDRAFT-JJL |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-AR | UA-6532 | 1 | 0
3 | 1701-AR | UA-6524 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | UA-6524 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-19 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-19 | 2007-01-25 |  | 2007-01-25 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1801-AR | UA-6525 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1801-MD | UA-6525 | 1 | 0 |  |  | 2007-01-19 | 2007-01-19 | 2007-01-29 |  |  | IC | 2007-01-19 | 2007-01-30 |  |  | 2007-01-30 | [5 empty] | 2007-01-02 | [14 empty] | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08
3 | 1201-AR | UA-6526 | 1 | 0 |  | WA | [30 empty] | 2007-03-30
|  | UA-6526 | 1 | 0 | CHECK W/ HT-NOT ON FINAL 2101-AR | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
1 | 1501-AR | UA-6527 | 1 | 0 |  | DR | 2007-02-14 | 2007-03-02 |  |  |  | DG | 2007-02-14 | [23 empty] | 2007-03-30
|  | UA-6529 | 1 | 0
|  | UA-6530 | 1 | 0
4 | 1401-AR | UA-6531 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27
[8 empty] | 2006-11-23 | 2006-11-27 | - |  | WAP | 2006-11-23 | 2006-11-27 |  | 2007-02-20 | 2007-02-20 | 2007-02-20 |  |  |  |  | 2007-01-30 |  | 2007-01-30 | WAP | 2007-02-09 | BACKCHECK-RO | 2007-02-09 | 2007-02-09 | 2007-02-14 | 2007-02-14 | 2007-02-20 | A
|  | UA-6532 | 1 | 0
3 | 1201-AR | WBF-7001 | 1 | 0 |  | WA | 2007-02-08 | 2007-02-08 | 2007-02-16 |  |  | W/ KY | 2007-02-20 | 2007-02-16 | [22 empty] | 2007-03-30
3 | 1201-AR | WBF-7002 | 1 | 0 |  | WA | 2007-02-08 | 2007-02-08 | 2007-02-16 |  |  | W/ KY | 2007-02-20 | 2007-02-16 | [22 empty] | 2007-03-30
4 | 2101-MD | WBF-7002 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | DG | 2006-11-23 | 2007-01-27 |  | 2007-02-13 | 2007-02-14 |  |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 | BACKDRAFT-AZ |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
[8 empty] | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | DG | 2006-11-23 | 2007-01-27 | 2007-01-15 | 2007-02-13 | 2007-02-14 | 2007-02-14 |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 | BACKDRAFT-AZ |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-15 | A
4 | 2101-AR | WBF-7002 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | WBF-7004 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | WBF-7004 | 2 | 0 |  | AZ | 2007-02-23
4 | 2101-AR | WBF-7005 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-AR | WBF-7006 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-AR | WBF-7007 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-AR | WBF-7008 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
[8 empty] | 2006-11-23 | 2006-11-27 | - |  | DG | 2006-11-23 | 2007-01-27 |  | 2007-02-13 | 2007-02-14 |  |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A
[8 empty] | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | DG | 2006-11-23 | 2007-01-27 | 2007-01-15 | 2007-02-13 | 2007-02-14 | 2007-02-14 |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A
[8 empty] | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | DG | 2006-11-23 | 2007-01-27 | 2007-01-15 | 2007-02-13 | 2007-02-14 | 2007-02-14 |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A
[8 empty] | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | DG | 2006-11-23 | 2007-01-27 | 2007-01-15 | 2007-02-13 | 2007-02-14 | 2007-02-14 |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A
[8 empty] | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | DG | 2006-11-23 | 2007-01-27 | 2007-01-15 | 2007-02-13 | 2007-02-14 | 2007-02-14 |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A
4 | 2101-AR | WBF-7009 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-MD | WBF-7009 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | DG | 2006-11-23 | 2007-01-27 |  | 2007-02-13 | 2007-02-14 |  |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 2101-AR | WBF-7010 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-MD | WBF-7010 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | DG | 2006-11-23 | 2007-01-27 |  | 2007-02-13 | 2007-02-14 |  |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 2101-AR | WBF-7011 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-MD | WBF-7011 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | DG | 2006-11-23 | 2007-01-27 |  | 2007-02-13 | 2007-02-14 |  |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 2101-AR | WBF-7012 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-MD | WBF-7012 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | DG | 2006-11-23 | 2007-01-27 |  | 2007-02-13 | 2007-02-14 |  |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
3 | 1201-AR | WBF-7013 | 1 | 0 |  | WA | [30 empty] | 2007-03-30
4 | 1403-AR | WBF-7013 | 1 | 0
[8 empty] | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A
|  | WBF-7013 | 1 | 0 | CHECK W/ HT-NOT ON FINAL 2101-AR | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-MD | WBF-7013 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | DG | 2006-11-23 | 2007-01-27 |  | 2007-02-13 | 2007-02-14 |  |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-AR | WBF-7014 | 1 | 0
[8 empty] | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A
1 | 1601-AR | WBF-7014 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | WBF-7014 | 1 | 0 | SHT 2 DEL; DWG INCORPORATED TO SHT 1 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13 | 1 | BACKDRAFT-JJL 11/1/7 | 2007-01-15 | 2007-01-15 | 2 |  | 2007-01-30 | 2007-01-30 | 3 |  | 2007-05-11 | 2007-05-11
1 | 1601-AR | WBF-7015 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7015 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7015 | 2 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-AR | WBF-7015 | 3 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7015 | 2 | 0 | WAS WBF-7015-03 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7016 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7016 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7016 | 2 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7016 | 2 | 0 | WAS WBF-7016-03 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7017 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7017 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7017 | 2 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-AR | WBF-7017 | 3 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7017 | 2 | 0 | WAS WBF-7017-03 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7018 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7018 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7018 | 2 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7018 | 2 | 0 | WAS WBF-7018-03 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7019 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7019 | 1 | 0 | WAS WBF-7019-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7019 | 2 | 0 |  | JJL | [34 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7020 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7020 | 1 | 0 | WAS WBF-7020-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7020 | 2 | 0 |  | JJL | [34 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7021 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7021 | 1 | 0 | WAS WBF-7021-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7021 | 2 | 0 |  | JJL | [34 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7022 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7022 | 1 | 0 | WAS WBF-7022-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7022 | 2 | 0 |  | JJL | [34 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7023 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | WBF-7023 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13 | 1 |  | 2007-05-11 | 2007-05-11
|  | WBF-7024 | 1 | 0
1 | 1503-AR | WBF-7025 | 1 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | WBF-7025 | 2 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WBF-7026 | 1 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WBF-7026 | 2 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | WBF-7027 | 1 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | WBF-7027 | 2 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | WBF-7028 | 1 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | WBF-7028 | 2 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WBF-7029 | 1 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WBF-7029 | 2 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WBF-7030 | 1 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WBF-7030 | 2 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1601-MD | WBF-7031 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
|  | WBF-7032 | 1 | 0
1 | 1601-AR | WBF-7033 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | WBF-7033 | 1 | 0 | WAS WBF-7033-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
|  | WBF-7034 | 1 | 0
1 | 1601-AR | WBF-7035 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | WBF-7035 | 1 | 0 | WAS WBF-7035-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
|  | WBF-7036 | 1 | 0
1 | 1601-AR | WBF-7037 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | WBF-7037 | 1 | 0 | WAS WBF-7037-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
|  | WBF-7038 | 1 | 0
1 | 1601-AR | WBF-7039 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | WBF-7039 | 1 | 0 | WAS WBF-7039-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7040 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7040 | 2 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7041 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7042 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7042 | 2 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7043 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7044 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7044 | 2 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7045 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7046 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7046 | 2 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7047 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7048 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | WBF-7048 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-13 | 2006-12-13
4 | 2101-AR | WBF-7048 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
1 | 1601-MD | WBF-7049 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7050 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7051 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7052 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7053 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7054 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13 | 1 | BACKDRAFT-JJL 11/1/7 | 2007-01-15 | 2007-01-15
1 | 1601-MD | WBF-7055 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7056 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7057 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7058 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7058 | 2 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
| 2101-AR | WBF-7061 | 1 | 0
4 | 2101-AR | WBF-7062 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
4 | 2101-AR | WBF-7062 | 2 | 0 |  | AZ | 2007-02-23
4 | 2101-MD | WBF-7062 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | DG | 2006-11-23 | 2007-01-27 |  | 2007-02-13 | 2007-02-14 |  |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-AR | WBF-7067 | 1 | 0
4 | 1403-MD | WBF-7067 | 1 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
[8 empty] | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A
|  | WBF-7068 | 1 | 0
4 | 1404-MD | WBF-7069 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1404-MD | WBF-7070 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1402-AR | WBF-7073 | 1 | 0 |  | RO
4 | 1402-AR | WBF-7073 | 2 | 0 |  | RO
4 | 1402-MD | WBF-7073 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 |  |  | WAP | 2007-01-19 | 2007-01-26 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1402-AR | WBF-7074 | 1 | 0 |  | RO
4 | 1402-AR | WBF-7075 | 1 | 0 |  | RO
4 | 1402-AR | WBF-7077 | 1 | 0 |  | RO
4 | 1402-AR | WBF-7078 | 1 | 0 |  | RO
4 | 1402-AR | WBF-7080 | 1 | 0 |  | RO
4 | 1402-AR | WBF-7081 | 1 | 0 |  | RO
4 | 2101-MD | WBF-7083 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | DG | 2006-11-23 | 2007-01-27 | 2007-01-15 | 2007-02-13 | 2007-02-14 | 2007-02-14 |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 2101-MD | WBF-7084 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | DG | 2006-11-23 | 2007-01-27 | 2007-01-15 | 2007-02-13 | 2007-02-14 | 2007-02-14 |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 2101-MD | WBF-7085 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | DG | 2006-11-23 | 2007-01-27 | 2007-01-15 | 2007-02-13 | 2007-02-14 | 2007-02-14 |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 2101-MD | WBF-7086 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | DG | 2006-11-23 | 2007-01-27 | 2007-01-15 | 2007-02-13 | 2007-02-14 | 2007-02-14 |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
1 | 1601-AR | WBF-7090 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | WBF-7090 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13 | 1 |  | 2007-03-14 | 2007-03-14
|  | WBF-7091 | 1 | 0
|  | WBF-7092 | 1 | 0
4 | 1403-MD | WBF-7093 | 1 | 0 | NEW | RO | 2007-02-08 | 2007-02-08 | 2007-02-20 | 2007-02-08 | 2007-02-16 |  |  | 2007-02-20 | 2007-02-16 | [9 empty] | 2007-02-08 | DG |  | BACKDRAFT-JJL |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | WBF-7094 | 1 | 0 | NEW | RO | 2007-02-08 | 2007-02-08 | 2007-02-20 | 2007-02-08 | 2007-02-16 |  |  | 2007-02-20 | 2007-02-16 | [9 empty] | 2007-02-08 | DG |  | BACKDRAFT-JJL |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | WBF-7095 | 1 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1404-MD | WBF-7095 | 1 | 0 | NEW | [27 empty] | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | WBF-7096 | 1 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1404-MD | WBF-7096 | 1 | 0 | NEW | [27 empty] | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1403-MD | WBF-7097 | 1 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1404-MD | WBF-7097 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
[8 empty] | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A
4 | 1403-MD | WBF-7098 | 1 | 0 |  | RO | 2007-01-17 | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 1404-MD | WBF-7098 | 1 | 0 |  |  | 2007-01-17 | 2007-01-17 | 2007-01-25 | 2007-01-17 | 2007-01-31 | WAP | 2007-01-17 | 2007-01-26 | 2007-01-31 | [7 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
[8 empty] | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A
[8 empty] | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | DG | 2006-11-23 | 2007-01-27 | 2007-01-15 | 2007-02-13 | 2007-02-14 | 2007-02-14 |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A
4 | 2101-AR | WBF-7099 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-AR | WBF-7100 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-MD | WBF-7100 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | - |  | DG | 2006-11-23 | 2007-01-27 |  | 2007-02-13 | 2007-02-14 |  |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
4 | 2101-MD | WBF-7101 | 1 | 0 |  |  | 2006-11-23 | 2006-11-23 | 2006-11-27 | 2006-11-23 | 2007-01-15 | DG | 2006-11-23 | 2007-01-27 | 2007-01-15 | 2007-02-13 | 2007-02-14 | 2007-02-14 |  | BACKDRAFT-AZ |  | 2007-02-13 | 2007-02-15 |  | 2007-02-15 | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | A |  |  |  | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
1 | 1601-MD | WBF-7102 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7102 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7102 | 2 | 0 | WAS WBF-7102-03 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-AR | WBF-7102 | 2 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-AR | WBF-7103 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 | 2007-01-18 | 2007-01-31 | DG | 2007-01-18 | 2007-01-22 | 2007-01-31 |  |  | 2007-01-31 | [18 empty] | 2007-03-30
1 | 1601-MD | WBF-7103 | 1 | 0 | WAS WBF-7103-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7103 | 2 | 0 |  | JJL | [34 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7104 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7104 | 2 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7105 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7106 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | 2006-11-06 | 2006-12-07 | DG | 2006-11-06 | 2006-11-14 | 2006-12-07 | [7 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601-MD | WBF-7107 | 1 | 0 |  | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
|  | WBF-7108 | 1 | 0
1 | 1601-AR | WBF-7109 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | WBF-7109 | 1 | 0 | WAS WBF-7109-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
4 | 2101-AR | WBF-7120 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
1 | 1501-AR | WBF-7121 | 1 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WBF-7121 | 2 | 0 |  | DR | 2006-12-14 | 2007-03-02 |  |  |  | DG | 2006-12-14 |  |  | 2007-02-23 |  |  | 2007-01-12 | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
4 | 2101-AR | WBF-9001 | 1 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-AR | WBF-9001 | 2 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-AR | WBF-9001 | 3 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-AR | WBF-9001 | 4 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 | 2007-02-23 | 2007-03-06 | W/ KY | 2007-02-23 | 2007-02-26 | 2007-03-07
4 | 2101-AR | WBF-9001 | 5 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
|  | WBF-9031 | 1 | 0
|  | WBF-9031 | 1 | 0
|  | WBF-9032 | 1 | 0
|  | WBF-9032 | 1 | 0
|  | WBF-9033 | 1 | 0
|  | WBF-9033 | 1 | 0
|  | WBF-9039 | 1 | 0
|  | WBF-9040 | 1 | 0
|  | WBF-9042 | 1 | 0
|  | WBF-9044 | 1 | 0
4 | 1402-MD | WS-7501 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 |  |  | WAP | 2007-01-19 | 2007-01-26 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1402-AR | WS-7501 | 1 | 0 |  | RO
1 | 1503-AR | WS-7503 | 1 | 0 |  | DR | 2007-02-23 | 2007-03-02 |  | 2007-02-23 | 2007-03-06 | DG | 2007-02-23 |  | 2007-03-07 | [21 empty] | 2007-03-30
1 | 1503-AR | WS-7503 | 2 | 0 |  | DR | 2007-02-23 | 2007-03-02 |  |  |  | DG | 2007-02-23 | [23 empty] | 2007-03-30
1 | 1503-AR | WS-7504 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 | [23 empty] | 2007-03-30
4 | 1402-AR | WS-7505 | 1 | 0 |  | RO
4 | 1402-MD | WS-7505 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 |  |  | WAP | 2007-01-19 | 2007-01-26 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 2101-AR | WS-7505 | 1 | 0 |  | AZ | 2007-02-23
4 | 2101-AR | WS-7505 | 2 | 0 |  | AZ | 2007-02-23
4 | 2101-AR | WS-7505 | 3 | 0 |  | AZ | 2007-02-23 | 2007-02-23 | 2007-02-26 |  |  | W/ KY | 2007-02-23 | 2007-02-26
|  | WS-7506 | 1 | 0
|  | WS-7507 | 1 | 0
|  | WS-7510 | 1 | 0
4 | 1402-AR | WS-7512 | 1 | 0 |  | RO
4 | 1402-MD | WS-7512 | 1 | 0 |  | RO | 2007-01-19 | 2007-01-19 | 2007-01-25 |  |  | WAP | 2007-01-19 | 2007-01-26 |  | 2007-02-05 | 2007-02-20 |  |  | BACKDRAFT-RO |  | 2007-02-05 | 2007-02-07 |  | 2007-02-07 | WAP | 2007-02-13 | BACKDRAFT-RO |  | 2007-02-13 |  |  | 2007-02-20 | A |  |  |  | 2007-02-21 | 2007-02-20 | [5 empty] | 2007-02-28
4 | 1403-AR | WS-7512 | 1 | 0
[8 empty] | 2007-01-17 | 2007-01-25 |  |  | WAP | 2007-01-17 | 2007-01-26 | [8 empty] | 2007-02-06 |  | 2007-02-06 | DG |  |  |  | 2007-02-14 |  |  | 2007-02-21 | A
|  | WS-7512 | 1 | 0
1 | 1501-AR | WS-7514 | 1 | 0 |  | DR | 2007-02-23 | 2007-03-02 |  | 2007-02-23 | 2007-03-06 | DG | 2007-02-23 |  | 2007-03-07 | [21 empty] | 2007-03-30
1 | 1502-AR | WS-7514 | 2 | 0 |  | DR | 2007-02-23 | 2007-03-02 |  |  |  | DG | 2007-02-23 | [23 empty] | 2007-03-30
1 | 1501-AR | WS-7515 | 1 | 0 |  | DR | [30 empty] | 2007-03-30
4 | 1307-MD | WW-8502 | 1 | 0 |  | HT | 2007-02-08 | 2007-02-08 | 2007-02-20 |  |  | HT | 2007-02-08 | 2007-02-20 | [12 empty] | 2007-02-21 | A | [9 empty] | 2007-02-21 | 2007-02-22 | [5 empty] | 2007-02-28
1 | 1503-AR | WW-8502 | 1 | 0 |  | DR | [30 empty] | 2007-03-30
1 | 1503-AR | WW-8503 | 1 | 0 |  | DR | [30 empty] | 2007-03-30
|  | WW-8505 | 1 | 0
3 | 1701-AR | WW-8506 | 1 | 0 |  | AZ | 2007-02-07 | 2007-02-07 | 2007-02-22 |  |  | W/ KY | 2007-02-20 | 2007-02-22 | [22 empty] | 2007-03-30
3 | 1701-MD | WW-8506 | 1 | 0 |  | AZ | 2007-01-10 | 2007-01-12 | 2007-01-16 |  |  | WA | 2007-01-10 | 2007-01-16 |  | 2007-01-19 | 2007-01-17 |  |  | BACKDRAFT-AZ |  | 2007-01-19 | 2007-01-25 |  | 2007-01-25 | WA | 2007-01-25 | BACKDRAFT - AZ |  | 2007-01-25 | [6 empty] | 2007-01-02 | 2007-01-05 | 2007-01-05 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 1 |  | 2007-05-11 | 2007-05-11
1 | 1503-AR | WW-8509 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1503-AR | WW-8509 | 2 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
1 | 1601-AR | WW-8509 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | WW-8509 | 1 | 0 | WAS WW-8509-02 | JJL | 2006-11-06 | 2006-11-06 | 2006-11-14 | - |  | DG | 2006-11-06 | 2006-11-14 | [8 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
|  | WW-8511 | 1 | 0 | CHECK W/ DR-NOT ON FINAL 1503-AR | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15
1 | 1601-AR | WW-8511 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
|  | WW-8518 | 1 | 0
|  | WW-8519 | 1 | 0
|  | WW-8529 | 1 | 0
|  | WW-8530 | 1 | 0
|  | WW-8531 | 1 | 0
|  | WW-8532 | 1 | 0
1 | 1501-AR | WW-8533 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WW-8534 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | WW-8535 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | WW-8536 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | WW-8537 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | WW-8538 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | WW-8539 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | WW-8540 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | WW-8541 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | WW-8542 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | WW-8543 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | WW-8544 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | WW-8545 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | WW-8546 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WW-8547 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WW-8548 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WW-8550 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WW-8551 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1502-AR | WW-8552 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | WW-8553 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1601-AR | WW-8554 | 1 | 0 |  | JJL | 2007-01-18 | 2007-01-18 | 2007-01-22 |  |  | DG | 2007-01-18 | 2007-01-22 | [22 empty] | 2007-03-30
1 | 1601-MD | WW-8554 | 1 | 0 | NEW | JJL | [16 empty] | 2006-11-23 |  | 2006-11-23 |  | 2006-12-01 |  | 2006-12-01 | [8 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 |  | WW-8555 | 1 | 0
1 | 1501-AR | WW-8555 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | WW-8556 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1503-AR | WW-8557 | 1 | 0 |  | DR | 2007-02-15 | 2007-03-02 |  |  |  | DG | 2007-02-15 | [23 empty] | 2007-03-30
4 | 1402-AR | WW-8559 | 1 | 0 |  | RO
4 | 1302-AR | WW-8560 | 1 | 0 |  | GM | 2007-02-20 | 2007-02-27 | 2007-03-01 |  |  | AK | 2007-02-27 | 2007-03-01 | [22 empty] | 2007-03-30
1 | 1501-AR | WW-8565 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
1 | 1501-AR | WW-8566 | 1 | 0 |  | DR | 2007-01-18 | 2007-03-02 |  |  |  | DG | 2007-01-18 |  |  | 2007-02-23 |  |  |  | BACKDRAFT-DR |  | 2007-02-23 | [14 empty] | 2007-03-30
|  | WW-8567 | 1 | 0
|  | WW-8568 | 1 | 0
|  | WW-8569 | 1 | 0
Note on AG65: msabater: re-submission
Note on AG66: msabater: re-submission
Note on AG290: msabater: re-submission
Note on AG291: msabater: re-submission
Note on AM293: msabater: replaced dwg due to changes made by Stress
Note on AM485: msabater: 6-Feb-07 replaced dwg due to changes made by Stress
Note on AN485: msabater: originally hold replaced dwg w/o hold
Note on AM645: msabater: 6-Feb-07 replaced dwg due to changes made by Stress
Note on AM727: msabater: 6-Feb-07 replaced dwg due to changes made by Stress
Note on AM816: msabater: replaced dwg due to changes made by Stress
Note on AM818: msabater: replaced dwg due to changes made by Stress

## GA log
CONSTRUCTION PACKAGE NO. | GA NUMBER |  | SHT No. | REV | DRAWING TITLE | ORIGINAL DRAWING | [17 empty] | COMMENTS | 1ST BACK DRAFT DRAWING | [6 empty] | 2ND BACK DRAFT DRAWING | [5 empty] | TO SQUAD CHECK | TO STRESS | ISSUE COPY FOR SIGNATURE |  |  |  |  | SIGNED ISSUE PLOTS | REV | COMMENTS | DATE RECEIVED | SIGNED ISSUE PLOTS | REV | COMMENTS | DATE RECEIVED | SIGNED ISSUE PLOTS
[6 empty] | DSGNR | DATE RECEIVED | MAT'LS CHECK |  | BERMAC CHECK |  | PIPING CHECK | [8 empty] | AREA LEAD / DSGNR |  |  |  | PIPING BACK-CHECK |  |  |  | AREA LEAD |  |  | PIPING BACK-CHECK |  | APPROVED OR DISAPPROVED | AREA LEAD |  |  |  |  | PIPING |  | STRESS |  | ENG'R
| UNIT No. | DRAWING NO. | SHT No. |  |  |  |  | OUT | IN | OUT | IN | OUT |  |  |  | IN |  |  | PIPING COPY SENT TO STRESS FOR 2nd REVIEW | APPROVED OR DISAPPROVED | OUT |  | IN | (REASON FOR HOLDS) | OUT | CHKR | IN | APPROVED OR DISAPPROVED | OUT |  | IN | OUT | IN |  | OUT |  | IN |  |  | OUT | IN | OUT | IN | OUT | DWF FILES ISSUED TO DOC CTRL |  |  |  | OUT TO DOCUMENT CONTROL |  |  |  | OUT TO DOCUMENT CONTROL
[12 empty] | CHKR | ORIG | RETURNED COPIES FROM
[14 empty] | MAT'LS | BERMAC | ORIG | MAT'LS | BERMAC |  |  | LEAD | FOR BACKDRAFT | [6 empty] | LEAD | FOR BACKDRAFT |  |  |  |  | LEAD | FOR BACKDRAFT
2 | 1101 | PEP-U1-230-2001 | 1 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1101 GRADE TO EL. 104600 PIPING PLAN | KF | 2006-12-13 |  |  |  |  | HT | 2006-12-13 | [24 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1101 | PEP-U1-230-2001 | 2 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1101 AT T.O.S. EL. 104915 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-04 |  |  |  | BAKDRAFT - KF | 2007-01-04 | 2007-01-04 | [15 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1101 | PEP-U1-230-2001 | 3 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1101 AT T.O.S. EL. 106745 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-15 |  |  |  | BACKDRAFT- | 2007-01-15 | [16 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1101 | PEP-U1-230-2001 | 4 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1101 AT T.O.S. EL. 108575 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-04 |  |  |  | BACKDRAFT-WA | 2007-01-04 | 2007-01-04 | 2007-01-08 |  | 2007-01-08 | WAP |  |  |  |  | 2007-01-19 | 2007-01-19 | [5 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1101 | PEP-U1-230-2001 | 5 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1101 GRADE TO EL. 104600 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
2 | 1102 | PEP-U1-230-2002 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1102 GRADE TO EL. 104620 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
2 | 1102 | PEP-U1-230-2002 | 2 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1102 AT T.O.S. EL. 104915 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-04 |  |  |  | BAKDRAFT - KF | 2007-01-04 | 2007-01-04 | [15 empty] | 2007-01-23 | [6 empty] | 2007-01-26 | 1 |  | 2007-05-11 | 2007-05-11
2 | 1102 | PEP-U1-230-2002 | 3 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1102 AT T.O.S. EL. 106745 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-15 |  |  |  | BACKDRAFT- | 2007-01-15 | [16 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1102 | PEP-U1-230-2002 | 4 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1102 AT T.O.S. EL. 108575 PIPING PLAN | KF | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2006-12-06 |  |  |  | BACKDRAFT - KF | 2006-12-06 | 2006-12-06 | 2006-12-22 |  | 2006-12-22 |  | 2007-01-03 | 2ND BACKDRAFT - KF | 2007-01-03 | 2007-01-03 | [7 empty] | 2007-01-23 | [6 empty] | 2007-01-26 |  |  |  |  | 2 |  | 2007-05-11 | 2007-05-11
2 | 1102 | PEP-U1-230-2002 | 5 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1102 AT T.O.S. EL. 110405 PIPING PLAN | KF | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-04 |  |  |  | BACKDRAFT-JB | 2007-01-04 | 2007-01-04 | 2007-01-08 |  | 2007-01-08 | WAP |  |  |  |  | 2007-01-19 | 2007-01-19 | [5 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1107 | PEP-U1-230-2002 | 7 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1107 AT T.O.S. EL. 113720 PIPING PLAN | KF | 2006-11-21 | - | - | - | - | RO | 2006-11-21 |  |  | 2006-11-30 |  |  |  | BACKDRAFT - JJL | 2006-11-30 |  | 2006-12-18 |  | 2006-12-18 | AK | 2007-01-09 | BACKDRAFT-KF |  | 2007-01-09 | [7 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1107 | PEP-U1-230-2002 | 8 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1107 AT T.O.S. EL. 114785 PIPING PLAN | KF | 2006-11-21 | - | - | - | - | RO | 2006-11-21 |  |  | 2006-11-30 |  |  |  | BACKDRAFT - JJL | 2006-11-30 |  | 2006-12-18 |  | 2006-12-18 | AK | 2007-01-09 | BACKDRAFT-KF |  | 2007-01-09 | [7 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1107 | PEP-U1-230-2002 | 9 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1107 PSV MODULE ISOMETRIC VIEWS | KF | 2006-11-21 | - | - | - | - | RO | 2006-11-21 |  |  | 2006-11-30 |  |  |  | BACKDRAFT - JJL | 2006-11-30 |  | 2006-12-18 |  | 2006-12-18 | AK | 2007-01-09 | BACKDRAFT-KF |  | 2007-01-09 | [7 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1103 | PEP-U1-230-2003 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1103 GRADE TO EL. 104600 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
2 | 1103 | PEP-U1-230-2003 | 2 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1103 AT T.O.S. EL. 104915 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-04 |  |  |  | BAKDRAFT - KF | 2007-01-04 | 2007-01-04 | [15 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1103 | PEP-U1-230-2003 | 3 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1103 AT T.O.S. EL. 106745 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-15 |  |  |  | BACKDRAFT- | 2007-01-15 | [16 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1103 | PEP-U1-230-2003 | 4 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1103 AT T.O.S. EL. 108575 PIPING PLAN | KF | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2006-12-06 |  |  |  | BACKDRAFT - KF | 2006-12-06 | 2006-12-06 | 2006-12-22 |  | 2006-12-22 |  | 2007-01-03 | 2ND BACKDRAFT - KF | 2007-01-03 | 2007-01-03 | [7 empty] | 2007-01-23 | [6 empty] | 2007-01-26 |  |  |  |  | 2 |  | 2007-05-11 | 2007-05-11
2 | 1103 | PEP-U1-230-2003 | 5 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1103 AT T.O.S. EL. 110405 PIPING PLAN | KF | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-04 |  |  |  | BACKDRAFT-WA | 2007-01-04 | 2007-01-04 | 2007-01-08 |  | 2007-01-08 | WAP | [11 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1103 | PEP-U1-230-2003 | 6 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1103 AT T.O.S. EL. 110405 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
2 | 1104 | PEP-U1-230-2004 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1104 GRADE TO EL. 104600 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
2 | 1104 | PEP-U1-230-2004 | 2 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1104 AT T.O.S. EL. 104915 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-04 |  |  |  | BAKDRAFT - KF | 2007-01-04 | 2007-01-04 | [15 empty] | 2007-01-23 | [6 empty] | 2007-01-26 |  |  |  |  | 2 |  | 2007-05-11 | 2007-05-11
2 | 1104 | PEP-U1-230-2004 | 3 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1104 AT T.O.S. EL. 106745 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-15 |  |  |  | BACKDRAFT- | 2007-01-15 | [16 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1104 | PEP-U1-230-2004 | 4 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1104 AT T.O.S. EL. 108575 PIPING PLAN | KF | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2006-12-06 |  |  |  | BACKDRAFT - KF | 2006-12-06 | 2006-12-06 | 2006-12-22 |  | 2006-12-22 |  | 2007-01-03 | 2ND BACKDRAFT - KF | 2007-01-03 | 2007-01-03 | [7 empty] | 2007-01-23 | [6 empty] | 2007-01-26 |  |  |  |  | 2 |  | 2007-05-11 | 2007-05-11
2 | 1104 | PEP-U1-230-2004 | 5 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1104 AT T.O.S. EL. 110405 PIPING PLAN | KF | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-04 |  |  |  | BACKDRAFT-WA | 2007-01-04 | 2007-01-04 | 2007-01-08 |  | 2007-01-08 | WAP | [11 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1105 | PEP-U1-230-2005 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1105 GRADE TO EL. 104600 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
2 | 1105 | PEP-U1-230-2005 | 2 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1105 AT T.O.S. EL. 104915 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-04 |  |  |  | BAKDRAFT - KF | 2007-01-04 | 2007-01-04 | [15 empty] | 2007-01-23 | [6 empty] | 2007-01-26 |  |  |  |  | 2 |  | 2007-05-11 | 2007-05-11
2 | 1105 | PEP-U1-230-2005 | 3 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1105 AT T.O.S. EL. 106745 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-15 |  |  |  | BACKDRAFT- | 2007-01-15 | [16 empty] | 2007-01-23 | [6 empty] | 2007-01-26 | 1 |  | 2007-05-11 | 2007-05-11
2 | 1105 | PEP-U1-230-2005 | 4 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1105 AT T.O.S. EL. 108575 PIPING PLAN | KF | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2006-12-06 |  |  |  | BACKDRAFT - KF | 2006-12-06 | 2006-12-06 | 2006-12-22 |  | 2006-12-22 |  | 2007-01-03 | 2ND BACKDRAFT - KF | 2007-01-03 | 2007-01-03 | [7 empty] | 2007-01-23 | [6 empty] | 2007-01-26 |  |  |  |  | 2 |  | 2007-05-11 | 2007-05-11
2 | 1105 | PEP-U1-230-2005 | 5 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1105 AT T.O.S. EL. 110405 PIPING PLAN | KF | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-04 |  |  |  | BACKDRAFT-WA | 2007-01-04 | 2007-01-04 | 2007-01-08 |  | 2007-01-08 | WAP | [11 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1106 | PEP-U1-230-2006 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1106 GRADE TO EL. 104600 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
2 | 1106 | PEP-U1-230-2006 | 2 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1106 AT T.O.S. EL. 104915 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-04 |  |  |  | BAKDRAFT - KF | 2007-01-04 | 2007-01-04 | [15 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1106 | PEP-U1-230-2006 | 3 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1106 AT T.O.S. EL. 106745 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-15 |  |  |  | BACKDRAFT- | 2007-01-15 | [16 empty] | 2007-01-23 | [6 empty] | 2007-01-26
2 | 1106 | PEP-U1-230-2006 | 4 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1106 AT T.O.S. EL. 108575 PIPING PLAN | TDAH | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2006-12-06 |  |  |  | BACKDRAFT - KF | 2006-12-06 | 2006-12-06 | 2006-12-22 |  | 2006-12-22 |  | 2007-01-03 | 2ND BACKDRAFT - KF | 2007-01-03 | 2007-01-03 | [7 empty] | 2007-01-23 | [6 empty] | 2007-01-26 |  |  |  |  | 2 |  | 2007-05-11 | 2007-05-11
2 | 1106 | PEP-U1-230-2006 | 5 | 0 | SW 1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT E/W PIPERACK PEP-1106 AT T.O.S. EL. 110405 PIPING PLAN | KF | 2006-11-16 | - | - | - | - | HT | 2006-11-16 |  |  | 2007-01-04 |  |  |  | BACKDRAFT-WA | 2007-01-04 | 2007-01-04 | 2007-01-08 |  | 2007-01-08 | WAP | [11 empty] | 2007-01-23 | [6 empty] | 2007-01-26
[12 empty] | HT | 2006-12-13 |  |  | 2007-01-10 |  |  |  | BACKDRAFT-GM | 2007-01-10 | 2007-01-10
[8 empty] | - | - | - | - | HT | 2006-12-21 |  |  | 2007-01-10 |  |  |  | BACKDRAFT-GM | 2007-01-10 | 2007-01-10
[8 empty] | - | - | - | - | HT | 2006-11-20
3 | 1201 | PEP-U1-230-2007 | 4 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S PIPERACK PEP-1201 GRADE TO EL. 105550 AREA PIPING PLAN | [31 empty] | 2007-03-30
3 | 1202 | PEP-U1-230-2008 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S PIPERACK PEP-1202 GRADE TO EL. 105550 AREA PIPING PLAN | [31 empty] | 2007-03-30
[8 empty] | - | - | - | - | HT | 2006-12-21 |  |  | 2007-01-10 |  |  |  | BACKDRAFT-GM | 2007-01-10 | 2007-01-10
[8 empty] | - | - | - | - | HT | 2006-11-20
3 | 1203 | PEP-U1-230-2009 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S PIPERACK PEP-1203 GRADE TO EL. 105550 AREA PIPING PLAN | [31 empty] | 2007-03-30
[8 empty] | - | - | - | - | HT | 2006-12-21 |  |  | 2007-01-10 |  |  |  | BACKDRAFT-GM | 2007-01-10 | 2007-01-10
[8 empty] | - | - | - | - | HT | 2006-11-20
3 | 1204 | PEP-U1-230-2010 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S PIPERACK PEP-1204 GRADE TO EL. 105550 AREA PIPING PLAN | [31 empty] | 2007-03-30
[8 empty] | - | - | - | - | HT | 2006-12-21 |  |  | 2007-01-10 |  |  |  | BACKDRAFT-GM | 2007-01-10 | 2007-01-10
[8 empty] | - | - | - | - | HT | 2006-11-20
3 | 1205 | PEP-U1-230-2011 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S PIPERACK PEP-1205 GRADE TO EL. 105550 AREA PIPING PLAN | [31 empty] | 2007-03-30
[8 empty] | - | - | - | - | HT | 2006-12-21 |  |  | 2007-01-10 |  |  |  | BACKDRAFT-GM | 2007-01-10 | 2007-01-10
[8 empty] | - | - | - | - | HT | 2006-11-20
3 | 1206 | PEP-U1-230-2012 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S PIPERACK PEP-1206 GRADE TO EL. 105550 AREA PIPING PLAN | [31 empty] | 2007-03-30
[8 empty] | - | - | - | - | HT | 2006-12-21 |  |  | 2007-01-10 |  |  |  | BACKDRAFT-GM | 2007-01-10 | 2007-01-10
[8 empty] | - | - | - | - | HT | 2006-11-20
3 | 2100 | PEP-U1-230-2013 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S PIPERACK AT L.P. B.F.W BLDG- GRADE TO EL. 103745 PIPING PLAN | [31 empty] | 2007-03-30
3 | 2100 | PEP-U1-230-2013 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S AREA 2100 PIPERACK AT T.O.S. EL. 104000 PIPING PLAN | [31 empty] | 2007-03-30
3 | 2100 | PEP-U1-230-2013 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S PEP-2100 AT T.O.S. EL. 107790 PIPING PLAN | [31 empty] | 2007-03-30
3 | 2100 | PEP-U1-230-2014 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S AREA 2100 PIPERACK AT T.O.S. EL. 100058 PIPING PLAN | [31 empty] | 2007-03-30
3 | 2100 | PEP-U1-230-2014 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S AREA 2100 PIPERACK AT T.O.S. EL. 104000 PIPING PLAN | [31 empty] | 2007-03-30
3 | 2100 | PEP-U1-230-2014 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S PEP-2100 AT T.O.S. EL. 107790 PIPING PLAN | [31 empty] | 2007-03-30
3 | 2100 | PEP-U1-230-2015 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S AREA 2100 PIPERACK AT T.O.S. EL. 104000 PIPING PLAN | [31 empty] | 2007-03-30
3 | 2100 | PEP-U1-230-2015 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT N/S AREA 2100 PIPERACK AT T.O.S. EL. 107790 PIPING PLAN | [31 empty] | 2007-03-30
4 | 1307 | PEP-U1-230-2016 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT INLET MODULE PEP-1307 PIPING PLAN | JBB | 2007-02-07 | - | - | - | - | HT | 2007-02-07 | [9 empty] | 2007-02-20 |  | 2007-02-20 | HT | 2007-02-21 | BACKDRAFT-JBB |  | 2007-02-21 | 2007-02-21 |  | 2007-02-21 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1307 | PEP-U1-230-2016 | 9 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT INLET MODULE PEP-1307 ISOMETRIC VIEW | JBB | 2007-02-07 | - | - | - | - | HT | 2007-02-07 | [9 empty] | 2007-02-20 |  | 2007-02-20 | HT | 2007-02-21 | BACKDRAFT-JBB |  | 2007-02-21 | 2007-02-21 |  | 2007-02-21 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
|  | PEP-U1-230-2017 | 1 | 0
| 1501 | PEP-U1-230-2018 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PEP-1501 PIPERACK AT GRADE TO EL. 104600 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
1 | 1501 | PEP-U1-230-2018 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT UNIT 1501 PIPERACK AT T.O.S. EL. 104915 PIPING PLAN | JB | 2006-11-09 | - | - | - | - | HT | 2006-11-09 |  |  | 2006-11-28 |  |  |  | BACKDRAFT - JB | 2006-11-28 | 2006-11-29 | 2006-12-06 |  | 2006-12-06 | [15 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
| 1501 | PEP-U1-230-2018 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PEP-1501 PIPERACK AT T.O.S. EL. 106730 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
1 | 1501 | PEP-U1-230-2018 | 5 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT UNIT 1501 PIPERACK AT T.O.S. EL. 104915 PIPING PLAN DETAIL | JB | 2006-11-09 | - | - | - | - | HT | 2006-11-09 |  |  | 2006-11-28 |  |  |  | BACKDRAFT - JB | 2006-11-28 | 2006-11-29 | 2006-12-06 |  | 2006-12-06 | [15 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
| 1502 | PEP-U1-230-2019 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PEP-1502 PIPERACK AT GRADE TO EL. 103600 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
1 | 1502 | PEP-U1-230-2019 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT UNIT 1502 PIPERACK AT T.O.S. EL. 104915 PIPING PLAN | JB | 2006-11-09 | - | - | - | - | HT | 2006-11-09 |  |  | 2006-11-28 |  |  |  | BACKDRAFT - JB | 2006-11-28 | 2006-11-29 | 2006-12-06 |  | 2006-12-06 | [15 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
| 1502 | PEP-U1-230-2019 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PEP-1502 PIPERACK AT T.O.S. EL. 106730 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
1 | 1503 | PEP-U1-230-2020 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT UNIT 1503 PIPERACK AT T.O.S. EL. 104915 PIPING PLAN | JB | 2006-11-09 | - | - | - | - | HT | 2006-11-09 |  |  | 2006-11-28 |  |  |  | BACKDRAFT - JB | 2006-11-28 | 2006-11-29 | 2006-12-06 |  | 2006-12-06 | [15 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
| 1503 | PEP-U1-230-2020 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PEP-1503 PIPERACK AT T.O.S. EL. 106730 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
| 1504 | PEP-U1-230-2021 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PEP-1504 PIPERACK AT GRADE TO EL. 103600 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
1 | 1504 | PEP-U1-230-2021 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT UNIT 1504 PIPERACK AT T.O.S. EL. 104915 PIPING PLAN | JB | 2006-11-09 | - | - | - | - | HT | 2006-11-09 |  |  | 2006-11-28 |  |  |  | BACKDRAFT - JB | 2006-11-28 | 2006-11-29 | 2006-12-06 |  | 2006-12-06 | [15 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
| 1504 | PEP-U1-230-2021 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PEP-1504 PIPERACK AT T.O.S. EL. 106730 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
1 | 1505 | PEP-U1-230-2022 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT UNIT 1505 PIPERACK AT T.O.S. EL. 104915 PIPING PLAN | JB | 2006-11-09 | - | - | - | - | HT | 2006-11-09 |  |  | 2006-11-28 |  |  |  | BACKDRAFT - JB | 2006-11-28 | 2006-11-29 | 2006-12-06 |  | 2006-12-06 | [15 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-13 | 2006-12-13
| 1505 | PEP-U1-230-2022 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PEP-1505 PIPERACK AT T.O.S. EL. 106730 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
| 1506 | PEP-U1-230-2023 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PEP-1506 PIPERACK AT GRADE TO EL. 103600 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
1 | 1506 | PEP-U1-230-2023 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT UNIT 1506 PIPERACK AT T.O.S. EL. 104915 PIPING PLAN | JB | 2006-11-09 | - | - | - | - | HT | 2006-11-09 |  |  | 2006-11-28 |  |  |  | BACKDRAFT - JB | 2006-11-28 | 2006-11-29 | 2006-12-06 |  | 2006-12-06 | [15 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
| 1506 | PEP-U1-230-2023 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PEP-1506 PIPERACK AT T.O.S. EL. 106730 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
| 1507 | PEP-U1-230-2024 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PEP-1507 PIPERACK AT T.O.S. EL. 106739 AREA PIPING PLAN | JBB | 2006-11-09 | - | - | - | - | HT | 2006-11-09 |  |  | 2006-11-28 |  |  |  | BACKDRAFT - JB | 2006-11-28 | 2006-11-29 | [14 empty] | 2007-03-30
1 | 1507 | PEP-U1-230-2024 | 2-1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT UNIT 1507 PIPERACK AT T.O.S. EL. 104915 PIPING PLAN | JB | 2006-11-09 | - | - | - | - | HT | 2006-11-09 |  |  | 2006-11-28 |  |  |  | BACKDRAFT - JB | 2006-11-28 | 2006-11-29 | 2006-12-06 |  | 2006-12-06 | [15 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1507 | PEP-U1-230-2024 | 2-2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT UNIT 1507 PIPERACK AT T.O.S. EL. 105830 PIPING PLAN | JB | 2006-11-09 | - | - | - | - | HT | 2006-11-09 |  |  | 2006-11-28 |  |  |  | BACKDRAFT - JB | 2006-11-28 | 2006-11-29 | 2006-12-06 |  | 2006-12-06 | [15 empty] | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1500 | PEP-U1-230-2026 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT STEAM GEN H-4700 PIPING PLAN | JBB | 2007-01-30 |  |  |  |  | JJL | 2007-01-30 | [23 empty] | 2007-03-30
1 | 1500 | PEP-U1-230-2027 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT STEAM GEN H-4600 PIPING PLAN | JBB | 2007-01-30 |  |  |  |  | JJL | 2007-01-30 | [23 empty] | 2007-03-30
1 | 1500 | PEP-U1-230-2028 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT STEAM GEN H-4500 PIPING PLAN | JBB | 2007-01-30 |  |  |  |  | JJL | 2007-01-30 | [23 empty] | 2007-03-30
1 | 1500 | PEP-U1-230-2029 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT STEAM GEN H-4400 PIPING PLAN | JBB | 2007-01-30 |  |  |  |  | JJL | 2007-01-30 | [23 empty] | 2007-03-30
1 | 1500 | PEP-U1-230-2030 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT STEAM GEN H-4300 PIPING PLAN | JBB | 2007-01-30 |  |  |  |  | JJL | 2007-01-30 | [23 empty] | 2007-03-30
1 | 1500 | PEP-U1-230-2031 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT STEAM GEN H-4200 PIPING PLAN | JBB | 2007-01-30 |  |  |  |  | JJL | 2007-01-30 | [23 empty] | 2007-03-30
1 | 1500 | PEP-U1-230-2032 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT STEAM GEN H-4100 PIPING PLAN | JBB | 2007-01-30 |  |  |  |  | JJL | 2007-01-30 | [23 empty] | 2007-03-30
1 | 1500 & 1600 | PEP-U1-230-2033 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT INST. AIR RECEIVER / CHEM. INJ PACKAGE PIPING PLAN | JBB | 2007-01-30 |  |  |  |  | JJL | 2007-01-30 | [23 empty] | 2007-03-30
1 | 1601 | PEP-U1-230-2034 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT AREA 1601 ELEV 100150 - 102460 PIPING PLAN | KF | 2006-11-06 | - | - | - | - | DG | 2006-11-06 |  |  | 2006-11-29 |  |  |  | BACKDRAFT - KF | 2006-11-29 | 2006-11-29 | [15 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601 | PEP-U1-230-2034 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT AREA 1601 ELEV 102580 - 104650 PIPING PLAN | KF | 2006-11-06 | - | - | - | - | DG | 2006-11-06 |  |  | 2006-11-29 |  |  |  | BACKDRAFT - KF | 2006-11-29 | 2006-11-29 | [15 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601 | PEP-U1-230-2034 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT AREA 1601 ELEV 104650 - 109030 PIPING PLAN | KF | 2006-11-06 | - | - | - | - | DG | 2006-11-06 |  |  | 2006-11-29 |  |  |  | BACKDRAFT - KF | 2006-11-29 | 2006-11-29 | [15 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601 | PEP-U1-230-2034 | 4 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT AREA 1601 ISOMETRIC VIEWS | KF | 2006-11-06 | - | - | - | - | DG | 2006-11-06 |  |  | 2006-11-29 |  |  |  | BACKDRAFT - KF | 2006-11-29 | 2006-11-29 | [15 empty] | 2006-12-01 | 2006-12-04 |  | 2006-12-11 |  | 2006-12-11 | 2006-12-12 | 2006-12-13
1 | 1601 | PEP-U1-230-2035 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT HP BFW PUMPS P-3030 A/E PIPING PLAN | JBB | 2007-02-08 |  |  |  |  | DR | 2007-02-08 | [23 empty] | 2007-03-30
1 | 1601 | PEP-U1-230-2036 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT LAB / INSTRUMENT AIR ANNEX PIPING PLAN | JBB | 2007-02-08 |  |  |  |  | DR | 2007-02-08 | [23 empty] | 2007-03-30
4 | 1301 | PEP-U1-230-2038 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT SITE GAS SLUG CATCHER PEP-1301 PIPING PLAN | KF | 2007-02-07 | - | - | - | - | AK | 2007-02-07 |  |  | 2007-02-13 |  |  |  | BACKDRAFT - KF |  | 2007-02-13 |  |  |  |  | 2007-02-20 | A | [9 empty] | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1301 | PEP-U1-230-2038 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT SITE GAS SLUG CATCHER AREA 1301 PIPING PLAN | [31 empty] | 2007-03-30
4 | 1301 | PEP-U1-230-2038 | 9 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT SITE GAS SLUG CATCHER PEP-1301 ISOMETRIC VIEW | KF | 2007-02-07 | - | - | - | - | AK | 2007-02-07 |  |  | 2007-02-13 |  |  |  | BACKDRAFT - KF |  | 2007-02-13 |  |  |  |  | 2007-02-20 | A | [9 empty] | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1302 | PEP-U1-230-2039 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT FUEL GAS HEATER SKID PEP-1302 PIPING PLAN | KF | 2007-02-07 | - | - | - | - | AK | 2007-02-07 |  |  | 2007-02-13 |  |  |  | BACKDRAFT - KF |  | 2007-02-13 |  |  |  |  | 2007-02-20 | A | [9 empty] | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1302 | PEP-U1-230-2039 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT FUEL GAS HEATER SKID AREA 1302 PIPING PLAN | [31 empty] | 2007-03-30
4 | 1302 | PEP-U1-230-2039 | 9 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT FUEL GAS HEATER SKID PEP-1302 ISOMETRIC VIEW | KF | 2007-02-07 | - | - | - | - | AK | 2007-02-07 |  |  | 2007-02-13 |  |  |  | BACKDRAFT - KF |  | 2007-02-13 |  |  |  |  | 2007-02-20 | A | [9 empty] | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1303 | PEP-U1-230-2040 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT ANNULUS GAS SLUG CATCHER PEP-1303 PIPING PLAN | KF | 2007-02-07 | - | - | - | - | AK | 2007-02-07 |  |  | 2007-02-13 |  |  |  | BACKDRAFT - KF |  | 2007-02-13 |  |  |  |  | 2007-02-20 | A | [9 empty] | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1303 | PEP-U1-230-2040 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT ANNULUS GAS SLUG CATCHER AREA 1303 PIPING PLAN | [31 empty] | 2007-03-30
4 | 1303 | PEP-U1-230-2040 | 9 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT ANNULUS GAS SLUG CATCHER PEP-1303 ISOMETRIC VIEW | KF | 2007-02-07 | - | - | - | - | AK | 2007-02-07 |  |  | 2007-02-13 |  |  |  | BACKDRAFT - KF |  | 2007-02-13 |  |  |  |  | 2007-02-20 | A | [9 empty] | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1304 | PEP-U1-230-2041 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT FUEL GAS LET DOWN STATIONS PEP-1304 PIPING PLAN | KF | 2007-02-07 |  |  |  |  | AK | 2007-02-07 |  |  | 2007-02-13 |  |  |  | BACKDRAFT - KF |  | 2007-02-13 |  |  |  |  | 2007-02-20 | A | [9 empty] | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1304 | PEP-U1-230-2041 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT FUEL GAS LET DOWN STATIONS AREA 1304 PIPING PLAN | [31 empty] | 2007-03-30
4 | 1304 | PEP-U1-230-2041 | 9 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT FUEL GAS LET DOWN STATIONS PEP-1304 ISOMETRIC VIEW | KF | 2007-02-07 |  |  |  |  | AK | 2007-02-07 |  |  | 2007-02-13 |  |  |  | BACKDRAFT - KF |  | 2007-02-13 |  |  |  |  | 2007-02-20 | A | [9 empty] | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1305 | PEP-U1-230-2042 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PRODUCED GAS SEPARATOR PEP-1305 PIPING PLAN | KF | 2007-02-07 |  |  |  |  | AK | 2007-02-07 |  |  | 2007-02-13 |  |  |  | BACKDRAFT - KF |  | 2007-02-13 |  |  |  |  | 2007-02-20 | A | [9 empty] | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1305 | PEP-U1-230-2042 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PRODUCED GAS SEPARATOR AREA 1305 PIPING PLAN | [31 empty] | 2007-03-30
4 | 1305 | PEP-U1-230-2042 | 9 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PRODUCED GAS SEPARATOR PEP-1305 ISOMETRIC VIEW | KF | 2007-02-07 |  |  |  |  | AK | 2007-02-07 |  |  | 2007-02-13 |  |  |  | BACKDRAFT - KF |  | 2007-02-13 |  |  |  |  | 2007-02-20 | A | [9 empty] | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1306 | PEP-U1-230-2043 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT GAS BLDG PUMP MODULE PEP-1306 PIPING PLAN | KF | 2007-02-07 |  |  |  |  | AK | 2007-02-07 |  |  | 2007-02-13 |  |  |  | BACKDRAFT - KF |  | 2007-02-13 |  |  |  |  | 2007-02-20 | A | [9 empty] | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1306 | PEP-U1-230-2043 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT GAS PUMP MODULE AREA 1306 PIPING PLAN | [31 empty] | 2007-03-30
4 | 1306 | PEP-U1-230-2043 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT GAS BLDG PUMP MODULE AREA 1306 PLATFORM VIEWS | [31 empty] | 2007-03-30
4 | 1306 | PEP-U1-230-2043 | 9 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT GAS BLDG PUMP MODULE PEP-1306 ISOMETRIC VIEW | KF | 2007-02-07 |  |  |  |  | AK | 2007-02-07 |  |  | 2007-02-13 |  |  |  | BACKDRAFT - KF |  | 2007-02-13 |  |  |  |  | 2007-02-20 | A | [9 empty] | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1401 | PEP-U1-230-2044 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PRODUCED GAS CONDENSERS AREA 1401 PIPING PLAN | [31 empty] | 2007-03-30
4 | 1401 | PEP-U1-230-2044 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PRODUCED GAS CONDENSERS AREA 1401 PIPING PLAN | [31 empty] | 2007-03-30
4 | 1401 | PEP-U1-230-2044 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PRODUCED GAS CONDENSERS MODULE PEP-1401 PIPING PLAN | KF | 2007-02-07 |  |  |  |  | WAP | 2007-02-07 | [9 empty] | 2007-02-16 |  | 2007-02-16 | WAP |  |  |  |  | 2007-02-20 | 2007-02-20 | 2007-02-20 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1401 | PEP-U1-230-2044 | 4 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PRODUCED GAS CONDENSERS MODULE PEP-1401 PIPING PLAN | KF | 2007-02-07 |  |  |  |  | WAP | 2007-02-07 | [9 empty] | 2007-02-16 |  | 2007-02-16 | WAP |  |  |  |  | 2007-02-20 | 2007-02-20 | 2007-02-20 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1401 | PEP-U1-230-2044 | 5 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PRODUCED GAS CONDENSERS MODULE PEP-1401 ISOMETRIC VIEWS | KF | 2007-02-07 |  |  |  |  | WAP | 2007-02-07 | [9 empty] | 2007-02-16 |  | 2007-02-16 | WAP |  |  |  |  | 2007-02-20 | 2007-02-20 | 2007-02-20 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1401 | PEP-U1-230-2044 | 6 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PRODUCED GAS CONDENSERS AREA 1401 PIPING PLAN | [31 empty] | 2007-03-30
4 | 1401 | PEP-U1-230-2044 | 7 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PRODUCED GAS CONDENSERS AREA 1401 PIPING PLAN | [31 empty] | 2007-03-30
4 | 1401 | PEP-U1-230-2045 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT EMULSION AREA 1401 PIPING PLAN | [31 empty] | 2007-03-30
4 | 1401 | PEP-U1-230-2045 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT EMULSION AREA 1401 PLATFORM VIEWS | [31 empty] | 2007-03-30
4 | 1405 | PEP-U1-230-2046 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT EMULSION PUMP HOUSE PEP-1405 PIPING PLAN | JBB | 2007-02-07 |  |  |  |  | WAP | 2007-02-07 | [9 empty] | 2007-02-20 |  | 2007-02-20 | WAP |  |  |  |  | 2007-02-20 | 2007-02-20 | 2007-02-20 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
4 |  | PEP-U1-230-2046 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT EMULSION PUMP HOUSE AREA PIPING PLAN | [31 empty] | 2007-03-30
4 | 1405 | PEP-U1-230-2046 | 9 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT EMULSION PUMP HOUSE PEP-1405 ISOMETRIC VIEWS | JBB | 2007-02-07 |  |  |  |  | WAP | 2007-02-07 | [9 empty] | 2007-02-20 |  | 2007-02-20 | WAP |  |  |  |  | 2007-02-20 | 2007-02-20 | 2007-02-20 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1402 | PEP-U1-230-2047 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PROCESS BUILDING MODULE PEP-1402 PIPING PLAN | JBB | 2007-02-07 |  |  |  |  | WAP | 2007-02-07 | [9 empty] | 2007-02-20 |  | 2007-02-20 | WAP |  |  |  |  | 2007-02-20 | 2007-02-20 | 2007-02-20 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1402 | PEP-U1-230-2047 | 2 |  | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PROCESS BUILDING PEP-1402 AREA PIPING PLAN | [31 empty] | 2007-03-30
4 | 1402 | PEP-U1-230-2047 | 9 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PROCESS BUILDING MODULE PEP-1402 ISOMETRIC VIEWS | JBB | 2007-02-07 |  |  |  |  | WAP | 2007-02-07 | [9 empty] | 2007-02-20 |  | 2007-02-20 | WAP |  |  |  |  | 2007-02-20 | 2007-02-20 | 2007-02-20 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1403 | PEP-U1-230-2048 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT EMULSION/BFW EXCHANGER MODULE PEP-1403 PIPING PLAN | JBB | 2007-02-07 |  |  |  |  | KY | 2007-02-07 | [19 empty] | 2007-02-21 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1404 | PEP-U1-230-2048 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT EMULSION/BFW EXCHANGER MODULE PEP-1404 PIPING PLAN | JBB | 2007-02-07 |  |  |  |  | KY | 2007-02-07 | [19 empty] | 2007-02-21 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1404 | PEP-U1-230-2048 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT EMULSION/BFW EXCHANGER MODULE PEP-1404 PIPING PLAN | JBB | 2007-02-07 |  |  |  |  | KY | 2007-02-07 | [19 empty] | 2007-02-21 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
4 | 1403 | PEP-U1-230-2048 | 4 |  | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT EMULSION/BFW EXCHANGER MODULE PEP-1403 AREA PIPING PLAN | [31 empty] | 2007-03-30
4 | 1404 | PEP-U1-230-2048 | 5 |  | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT EMULSION/BFW EXCHANGER MODULE PEP-1404 AREA PIPING PLAN | [31 empty] | 2007-03-30
4 | 1403 & 1404 | PEP-U1-230-2048 | 9 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT PEP-1403 & PEP-1404 ISOMETRIC VIEWS | JBB | 2007-02-07 |  |  |  |  | KY | 2007-02-07 | [19 empty] | 2007-02-21 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
[8 empty] | - | - | - | - | WA | 2007-01-19 |  |  | 2007-01-24 |  |  |  | BACKDRAFT - KF |  | 2007-01-24 |  |  |  | WA | 2007-01-26 | BACKDRAFT - KF |  | 2007-01-26 | 2007-02-01
3 | 1700 | PEP-U1-230-2049 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT GLYCOL / UTILITY BLDG AREA 1700 PLATFORM VIEWS | [31 empty] | 2007-03-30
3 | 1700 | PEP-U1-230-2049 | 3 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT GLYCOL / UTILITY BLDG AREA 1700 PIPING PLAN | [31 empty] | 2007-03-30
[8 empty] | - | - | - | - | WA | 2007-01-19 |  |  | 2007-01-24 |  |  |  | BACKDRAFT - KF |  | 2007-01-24 |  |  |  | WA | 2007-01-26 | BACKDRAFT - KF |  | 2007-01-26 | 2007-02-01
[8 empty] | - | - | - | - | IC | 2007-01-29 |  |  | 2007-02-05 |  |  |  | BACKDRAFT - KF | [5 empty] | IC
3 | 1800 | PEP-U1-230-2050 | 2 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT FLARE KNOCKOUT BLDG AREA 1800 PIPING PLAN | [31 empty] | 2007-03-30
[8 empty] | - | - | - | - | IC | 2007-01-29 |  |  | 2007-02-05 |  |  |  | BACKDRAFT - KF | [5 empty] | IC
3 | 2100 | PEP-U1-230-2051 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT LP PUMP AREA 2100 PIPING PLAN | [31 empty] | 2007-03-30
4 | 2101 | PEP-U1-230-2052 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT LP BFW PUMP BLDG PEP-2100 PIPING PLAN | KF | 2007-02-07 |  |  |  |  | IC | 2007-02-07 |  |  | 2007-02-14 |  |  |  | BACKDRAFT-KF |  | 2007-02-14 |  |  |  | IC | 2007-02-15 | BACKDRAFT-KF |  | 2007-02-15 | 2007-02-15 | 2007-02-15 | 2007-02-16 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
4 | 2100 | PEP-U1-230-2052 | 2 |  | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT LP BFW PUMP BLDG AREA 2100 PIPING PLAN | [31 empty] | 2007-03-30
4 | 2101 | PEP-U1-230-2052 | 9 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT LP BFW PUMP BLDG PEP-2100 ISOMETRIC VIEW | KF | 2007-02-07 |  |  |  |  | IC | 2007-02-07 |  |  | 2007-02-14 |  |  |  | BACKDRAFT-KF |  | 2007-02-14 |  |  |  | IC | 2007-02-15 |  |  |  | 2007-02-15 | 2007-02-15 | 2007-02-16 | A |  |  |  | 2007-02-21 | [6 empty] | 2007-02-23
3 | 2100 | PEP-U1-230-2053 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT BFW TANK AREA 2100 PIPING PLAN | [31 empty] | 2007-03-30
3 | 2100 | PEP-U1-230-2054 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT BFW TANK AREA 2100 PIPING PLAN | [31 empty] | 2007-03-30
5 | 2000 | PEP-U1-230-2055 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT FLARE STACK AREA PEP-2000 PIPING PLAN | [31 empty] | 2007-03-30
5 | 2000 | PEP-U1-230-2056 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT FLARE STACK AREA PEP-2000 PIPING PLAN | [31 empty] | 2007-03-30
5 | 1900/2000 | PEP-U1-230-2057 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT FLARE STACK AREA 1900 / 2000 PIPING PLAN | [31 empty] | 2007-03-30
5 | 1900 | PEP-U1-230-2058 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT POND AREA 1900 PIPING PLAN | [31 empty] | 2007-03-30
5 | 1900 | PEP-U1-230-2059 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT POND AREA 1900 PIPING PLAN | [31 empty] | 2007-03-30
| 1501 | PEP-U1-230-2060 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT AREA 1501 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
| 1501 | PEP-U1-230-2061 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT AREA 1501 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
| 1502 | PEP-U1-230-2062 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT AREA 1502 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
| 1503 | PEP-U1-230-2063 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT AREA 1503 AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
| 1601 | PEP-U1-230-2064 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT STEAM GENERATOR BUILDING AREA 1601, 1503 AREA PIPING PLAN | JBB | 2007-02-08 |  |  |  |  | DR | 2007-02-08
| 1500 | PEP-U1-230-2064 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT INTERCONNECTING AREA UTILITIES - E/W PIPERACK AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
| 1601 | PEP-U1-230-2065 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT STEAM GENERATOR BUILDING AREA 1601 AREA PIPING PLAN | JBB | 2007-02-08 |  |  |  |  | DR | 2007-02-08
| 1500 | PEP-U1-230-2065 | 1 | 0 | SW1/4 SEC.14 TWP.67 RGE.3 W.4 MER. PEP PROJECT INTERCONNECTING AREA H.P. B.F.W. - E/W PIPERACK AREA PIPING PLAN | JBB | [30 empty] | 2007-03-30
[8 empty] | - | - | - | -
[8 empty] | - | - | - | -
Note on N41: msabater: re-submission orig released 21-Nov-06
Note on N45: msabater: re-submission orig released 21-Nov-06
Note on N48: msabater: re-submission orig released 21-Nov-06
Note on N51: msabater: re-submission orig released 21-Nov-06
Note on N54: msabater: re-submission orig released 21-Nov-06
Note on N57: msabater: re-submission orig released 21-Nov-06

## IFC log
IFC DATES
MODULE / OFF MOD | Package No. | Date Issued | Type | Area | No. of Sheets | HOLDS | Re-Issue (REV.1) | No. of Sheets | Re-Issue (REV.2) | No. of Sheets
MODULE
OFF - MODULE