## Sheet1
PIPING DESIGN & PLANT LAYOUT
| TEMPLATE | NO:
|  | TITLE: | MODEL REVIEW MATRIX
|  | DATE: |  |  | Rev #
| IFR MODEL (STUDY) | IFA MODEL (30%) |  | IFD MODEL (60%) |  | IFC MODEL (90%)
PRE REVIEW REQUIREMENTS (2 to 4 WEEKS PRIOR TO SCHEDULED REVIEW)
| Conduct a model readiness review and complete 10% checklist (By Project Engineer) - interdisciplinary review | Conduct a model readiness review and complete 30% checklist (By Project Engineer) - interdisciplinary review |  | Conduct a model readiness review and complete 60% checklist (By Project Engineer) - interdisciplinary review |  | Conduct a model readiness review and complete 90% checklist (By Project Engineer) - interdisciplinary review
| Determine participation list for the study model review | Model is opened to determine extent of progress and that it aligns with readiness checkslist |  | Model is opened to determine extent of progress and that it aligns with readiness checkslist |  | Assign outstanding tasks to team members leading up to the set model review date
| Assign outstanding tasks to team members leading up to the set model review date | Determine participation list for the 30% model review |  | Determine participation list for the 60% model review |  | Determine participation list for the 90% model review
| Review P&ID's against the model developed. Highlight P&ID's. | Review P&ID's against the model developed. Highlight P&ID's. |  | Review P&ID's against the model developed. Highlight P&ID's. |  | Review P&ID's against the model developed. Highlight P&ID's.
| Assess model review date and confirm "go" or "no go" | Assign outstanding tasks to team members leading up to the set model review date |  | Assign outstanding tasks to team members leading up to the set model review date |  | Assess model review date and confirm "go" or "no go"
| Project Engineer Signs Off on readiness | Assess model review date and confirm "go" or "no go" |  | Assess model review date and confirm "go" or "no go" |  | Project Engineer Signs Off on readiness
| Project Manager Signs off on readiness | Project Engineer Signs Off on readiness |  | Project Engineer Signs Off on readiness
|  | Project Manager Signs off on readiness |  | Project Manager Signs off on readiness
REVIEW OBJECTIVES
| Plant & Building escape routes | 3" and above large bore pipe routings |  | Finalize all inter-discipline designs |  | Review of 60% Model Review action items
| Identify Maintenance and Operating spacing requirements | Major Steel and Platforms |  | Review of IFA Model review action items |  | Freeze Steel
| Identify Major Maintenance and Operating platforms and walkways | Major Cable tray routings |  | Review 3" and below piping |  | Freeze Piping
| Overall plant safety | Set preliminary locations for insturmentation and panels. |  | Review Steel |  | Glycol Tracing Manifolds Complete
| Overall Constructability | Constructability Input |  | Finalize all critical piping locations (CV stations, truck out, meter runs) |  | Freeze Electrical
| Equipment location and operability | Maintainability Input |  | IFC Foundations
| Main Structure Locations | Operability Input |  | Review electrical equipment and cable tray
Large bore piping and piperack conceptual routing.
Major expansion loop locations
Review Plant grading runoff etc.
DESIGN PROGRESS REQUIRED (DATA INPUTS INTO MODEL)
PROCESS DESIGN
PFD & Mass Balance | IFA | IFD |  | - |  | -
P&ID's | IFR | IFD |  | IFD (Stick File) |  | IFC Ready, not stamped or issued
HAZOP | - | Completed with all issues resolved |  | Completed with all issues resolved |  | -
Process Studies | Major Studies Complete | All Studies Complete |  | - |  | -
Line Designation Table (Line List) | IFA | IFD |  | IFD (Stick File) |  | IFC
Piping Specifications | Approved
PIPING DESIGN
Plot Plan | IFA | IFD |  | IFD |  | IFC
Equipment Layout (Note 4) | Major Equipment -Modeled to preliminary information as blocks -Reserved Operating and Maintenance spacing identified | Major Equipment Locations -Finalized and modeled to first submission of drawings |  | Major Equipment modeled to Code 2 |  | Equipment modeled to Code 4 unless otherwise approved
Piping Stress Analysis | Critical lines requiring loops stress identified. | All lines 4" and above modeled and submitted to stress. |  | All lines to stress. |  | All stress complete and verified
Piping Design | All lines 6" and above are modeled and major loops identified. | 3" and above modeled |  | 2" and above designed and modeled |  | All lines and any changes from 60% model to 90 % model are re designed
HP Steam Valves and Flex Connections | As per P&ID | 3" and above are modeled |  | All valves are modeled to Code 2 |  | All valves are modeled to Code 4
Piperack Supports | Preliminary | All major supports modeled |  | All major supports modelled. |  | All supports designed and modeled
Anchors, Guides and Shoes | Not Started | 4" & above lines started |  | 2" & above lines degigned & modelled |  | All designed and modeled
In-Line Instruments | As per P&ID | Preliminarily modeled to catalogue data |  | Complete and modeled to Code 2 |  | All modeled to Code 4
Specialty Items (other than Flex Connections) | As per P&ID | Preliminary in lines modeled |  | Modeled to Catalogue Data |  | Modeled to Code 4 where applicable.
Glycol Tracing | Not Started | Manifolds and headers preliminarily laid out |  | Header and manifolds modeled |  | Header and manifolds designed and modeled.
HVAC (air make-up units if required) | Not Started | Major units modeled to preliminay data |  | Major units modeled to Code 2 All other units modeled prelim. |  | All units modeled to Code 4
Unit Heaters and Ventilation Fans | Not Started | Preliminary |  | Modeled to Catalogue Data |  | Modeled to Code 2
Modules Identified | Preliminary | Final |  | Final |  | Final
VENDOR INFORMATION
HP Steam Valves and Flex Connections | None | Vendor Dimensional Data for 4" and above |  | Code 2 |  | Code 4
Specialty Items | None | Preliminary |  | Catalogue Vendor Data |  | Code 4 where applicable
Equipment (Note 4) | Preliminary foot prints (from previous data) | Major Equipment to first submission drawings |  | Major Equipment to Code 2 |  | Major Equipment to Code 4
In-Line Instruments | None | Preliminarily modeled to catalogue data obtained from preferred vendors manuals |  | Complete and modeled to Code 2 |  | All modeled to Code 4
CIVIL DESIGN
Earthworks, roads, berms, ditches, etc. | Major Modeled | All Modeled |  | - |  | -
Piling Design | Preliminary | Preliminary |  | Modeled |  | Designed and Modeled (IFC)
Foundations (Major) | Preliminary | Preliminary modeled |  | Modeled |  | Designed and Modeled (IFC)
Undergrounds | Conceptual Layout modeled | Started |  | Modeled |  | Designed and Modeled (IFC)
Architectural Layout and Buildings | Preliminary building size modeled | Building size confirmed and modeled |  | Modeled |  | Designed and Modeled (IFC)
Major Steel (Racks and Structures) | Conceptual Layout modeled | Started |  | Modeled |  | Designed and Modeled
Maintenance Access, Walkways, and Platforms | Not Started | Modeled |  | Modeled |  | Designed and Modeled
Secondary Steel | Not Started | Started |  | Modeled |  | Designed and Modeled
Misc. Pipe Supports | Not Started | Started |  | Modeled |  | Designed and Modeled
ELECTRICAL / INSTRUMENTS
Cable Trays 8" and Above | Not Started | Routings and Drops sized and modeled on main racks and buildings |  | All spacing requirements for routing and drops modeled and confirmed |  | -
MCC Buildings | Preliminary footprints | Modeled |  | Designed and modeled |  | -
Power Transformers | Preliminary footprints | Modeled |  | Designed and modeled |  | -
Substations | Preliminary footprints | Modeled |  | Designed and modeled |  | -
Major panels and enclosures Outside of MCC Buildings | Not Started | Some modeled |  | Modeled |  | Designed and modeled
Building Lighting | Not Started | Started |  | Modeled |  | Designed and modeled
Area Lighting (Floodlight Poles Only) | Not Started | Started |  | Modeled |  | -
Underground Power Cables | Conceptual routing modeled | Designed and modeled |  | Checked and Modeled |  | Checked and Modeled
Overhead Power Lines ROW | Preliminary | ROW shown on model |  | - |  | -
Off Line & Remote Mounted Instruments | Not Started | Preliminary Modelled to Info Received from Instrumentation or Data Sheets |  | Designed & Modelled |  | All Instruments Verified & Modelled
Analyzer Panels | Not Started | Preliminary Modelled to Info Received from Instrumentation or Data Sheets |  | Designed & Modelled |  | All Instruments Verified & Modelled
Instrument Enclosures | Not Started | Preliminary Modelled to Info Received from Instrumentation or Data Sheets |  | Designed & Modelled |  | All Instruments Verified & Modelled
Vendor Information | N/A | Preliminary Information |  | Code 2 |  | Code 4
POST REVIEW DESIGN OBJECTIVES
| Freeze equipments locations | P&ID's IFD |  | Undergrounds IFC |  | Isometrics IFC
| Plot Plan IFD | LDT's IFD |  | Foundations IFC |  | GA's IFC
| Cable tray plan | Freeze Piping 4" and above |  | Piling drawings IFC |  | Structural Steel IFC
| MCC building(s)/ transformer yard IFD | Freeze Foundations |  | Freeze the model for piping, electrical, instrumentation. |  | Electrical IFC
| Freeze main piperack routings | Freeze piling |  |  |  | EHTand glycol tracing IFC
| Model Maintenance and Operating spacing requirements | Freeze Architectural |  | Architectural at IFB |  | Architectural IFF
| P&ID's IFD |  |  | P&ID IFC
| Line List IFA |  |  | Line List IFC
GROUND RULES
1. All model review comments shall be documented and assigned immediately following model review.
2. No changes to frozen items shall be initiated without approval through the change management process.
3. Personal preferences are not acceptable reasons for initiating a change. The following guidelines have been established for intiating a change:
-Design does not meet the design criteria for one of the disciplines
-Design does not meet accepted design practice for one of the disciplines
-Design does not meet plant operating standards or clients standards for fire protection, safe isolation of
equipment, operability, maintainability
-Design does not meet safety requirements
-Design does not meet What-If review recommendations
RECOMMENDED ATTENDIES
Model Facilitator | Piping Area Lead | Piping Area Lead |  | Piping Area Lead |  | Piping Area Lead
| Project Manager | Project Engineer(s) |  | Project Engineer(s) |  | Project Engineers(s)
| Project Engineer(s) | Client PM/PE
| Client PM/PE | Civil Discipline Lead |  | Civil Discipline Lead |  | Civil Discipline Lead
| Operations Rep. | Operations and Maintenance Rep.
| Construction Rep. | Electrical Lead |  | Electrical Lead |  | Electrical Lead (for elec WP's)
| Piping Design Lead | Instrument Lead |  | Instrument Lead |  | Instrument Lead
| Electrical Lead | Process Area Lead |  | Civil Design Lead |  | Civil Design Lead
| Process Area Lead | Construction Rep
| Civil Design Lead | Piping Technical Advisor |  | Piping Technical Advisor |  | Tracing Designers (optional)
| Piping Technical Advisor | Civil Design Lead
Note 1:
Note 2: | Code 2 is Correct & resubmit. Manufacturing may proceed subject to incorporating comments.
Note 3: | Code 4 is Information / record purposes only. Certified As Built.
Note 4: | Major equipment is any major equipment comprising of 90% of total equipment capital for project.
Note 5: | Exceptions to the criteria can be approved by the Project Managaer
Note 6: | Template data can be used, but must be stamped for approval of use